

Fortnightly Progress Report

SIDBI – PMU Maharashtra

Period –1st to 15th April 2023

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Maharashtra**  **Month & Year: April 2023**  **Fortnight Ending: 15th April, 2023** | **Report Summary**  This report includes the activities conducted by SIDBI - PMU for the  facilitation of MSME Ecosystem in the State of Maharashtra. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | Consultant | Abhay Ravetkar | 5th April 2021 (In Maharashtra PMU 4th Feb- 2023) |
| 2 | Business Analyst | Shital Shintre | 10th Oct 2022 |

**Details of State Nodal Connect - Name – Devraj Madam – 08425887836 (SIO)**

**Activities performed by PMU during fortnight ending 15th April 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of activities conducted** |
| **General Activities to facilitate project implementation** | |
| 1.**SCDF –**  **Skill Department**: PMU team is in continuous touch with officials of Skill development department. The DPR and file of Panvel ITI project have been approved by Finance Department and sent back to Skill Dev. Department. Now, Skill dev. Department will send the budgetary requirement and request for loan under SCDF to FD. PMU is following up with Department to move the file to FD post which, the Finance Department will be sign the Master agreement with SIDBI. PMU along with DGM, SIDBI is in continuous touch with the officials of Finance Department at the level of ACS, Principal Secretary and JS, Finance to explain about SCDF. Now they have agreed on signing of Master Agreement.    The format of MoU/Master Agreement for SCDF has been sent to Finance department by Legal department with their remarks on it, suggesting, to get approval of DCM office & then GR to be drafted & execute. PMU team with DGM, SIDBI met Secretary Finance for GR. PMU team prepared a note on SCDF guideline in Marathi Language & submitted it to FD to enable them to prepare a GR, FD officials have prepared a note to put up with DCM office to get Cabinet approval. PMU team visited Principal Secretary finance for taking the overview about file status of SCDF & requested to expedite the work.  **Energy Department** – PMU Team had meeting with Director, MSEDCL and their Finance team along with EDI, PMC senior officials. Director Finance, MSEDCL told SIDBI officials that, they have huge demand of funds for their projects. But they are sceptical about the process of the SCDF as Finance Department will not be taking the loan under SCDF for MSEDCL projects in their books of Accounts. During last meeting held with officials of MSEDCL it was understood that they are going to communicate with FD about requirement of MSEDCL & considering the loan under SCDF. Post this letter, there will be more clarity about MSEDCL projects to cover under SCDF.  **PWD-Roads**: PMU team had several meetings with Secretary PWD including the one had along with SIDBI GM for shortlisting of PWD projects under SCDF. PWD department have identified & selected proposal of Rs.1000 Cr. for considering under SCDF & same have been sent to their Departmental Head. The PWD project list file has been sent to Finance & Planning Department for their approval. it has now been approved by the Secretary PWD.  **SCDF Workshop :** PMU team followed up with the Finance department to get nomination for conference arranged by SIDBI on SCDF at Goa. Got nomination of ACS, Accounts & Treasury Dept. Updated him about SCDF implementation status in State. | |
| **2. State Industry Department meet :** Coordination with ONDC officials to participate to brief Industry line department about ONDC in State Industry departmental meet at Nasik to be held on 24th and 25th April 2023 | |
| **3**. **Prepared a Note on RAMP**: Note Prepared comprising of Present status of various activities & programmes for MSMEs in State, Challenges & Recommendations to be discussed in Stakeholders meeting proposed under the chairmanship of PS. Industries & Commerce. | |
| **4**. PMU submitted a draft action plan to DC about the monitoring of various schemes and have initiated a Fortnightly review where PMU will be submitting a monthly report to DC on development of various schemes. | |
| **5**. Study & work on comparison of Coir sector & policies of 4 States in India. | |

|  |
| --- |
| **Activities way forward** |
| 1. Follow up for State CGTMSE, ONDC, Fund of Fund Scheme implementation 2. Study & comparison of Coir schemes & sector across in India. 3. MOU with State Government for SCDF. 4. Monthly Planner for Department. |
| **Inputs of State Nodal Connect / Officer** |
| 1. Good work by SIDBI PMU Team |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** proved under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*