

Fortnightly Progress Report

SIDBI – PMU Maharashtra

Period – 1st to 15th February 2023

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Maharashtra**  **Month & Year: January 2023**  **Fortnight Ending: 15th February, 2023** | **Report Summary**  This Report includes the activities carried out by SIDBI - PMU for the  facilitation of MSME Ecosystem in the State of Maharashtra. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | Consultant | Abhay Ravetkar |  |
| 2 | Business Analyst | Shital Shintre | 10th Oct 2022 |

**Details of State Nodal Connect - Name – Devraj Madam – 08425887836 (SIO)**

**Activities performed by PMU during fortnight ending 15th February 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| **General Activities to facilitate project implementation** | |
| 1.SCDF –  Skill Department: PMU is in continuous touch and meeting various stakeholders in Skill Department for moving the file. With the current status first DPR and file of Panvel ITI is being approved by Finance and sent back to Skill Department. Skill Department will now be sending the budgetary requirement and request for loan under SCDF to Finance. PMU is following up with the Department to move the file to Finance and post which the Finance Department will be signing the master agreement. In 14th February 2023 the meeting was done with Finance Department in this meeting finance Department raise query now they clear all there query now the Department has ready to signing the Agreement within few days. Same day the Principal Secretary Miss Shaila madam held meeting with various department and give the suggestion to all department take a SIDBI loan. Now the Panvel ITI file send to legal department.  Energy Department – PMU had meeting with MSEDCL Director and Finance team along with EDI senior officials, Director Finance communicated that they need lot of funds but are unsure about the process of the SCDF as Finance Department won’t be taking the loan on their books. With the last meeting held, MSEDCL officials will be writing letter to P Sec Energy Department regarding the ongoing update on SCDF fund. Post this letter there will be more clarity.  PWD-Roads: PMU held various meetings few of them was along with SIDBI GM with Secretary PWD regarding the selection of projects. PWD department has selected 1000 cr proposal and are being approved by Minister to avail SCDF fund. This file will be sent to Finance & Planning on the list of new projects. PMU have meet the Secretary PWD now file is move to PWD department and singed by secretary of PWD then send by Finance department. PMU is following up with the department to move the file as soon as possible. | |
| 2. Green Finance – SIDBI PMU has sensitized the concept of SIDBIs Green Finance schemes to Industries Department. And have initiated that there shall be one such seminar on Green Finance schemes. PMU also facilitated the meeting with GM SIDBI and Department for the same. Department suggest that arrange one seminar for green finance scheme and invite all cluster and same industries to know the scheme. | |
| 3. Skilling initiative – PMU along with Department has planned to develop a concept on skilling the clusters and nearby ITIs which will help clusters to resolve their skilled manpower issues and for ITI students a live training and skilling session. Department has approached to SIDBI for the same. PMU will be soon developing a concept note. On Pilot basis selected cluster from Pune, like Auto, Tooling and Rubber where EDP training will be given the connection between skilled labour and industries will be established. This project will have established project linkages and enterprise creation for SIDBI & Industrial Department. | |
| 4. PMU arranged the meeting with Hon’ble Principal Secretary, Industries and SIDBI for CGTMSE | |
| 5. PMU help to the department for Industrial Investments Summit programme in Maharashtra and also prepaid a letter for SIDBI to join as Co-organizing institution | |
| 6. PMU working on ONDP to Maharashtra state | |

|  |
| --- |
| **Actionable and Support required** |
| 1. PWD projects screening 2. Yearly Planner for Department 3. ONDC |
| **Activities way forward** |
| 1. Following up on Skill file and meeting for Master Agreement preparation. |
| **Inputs of State Nodal Connect / Officer** |
| 1. Good work by SIDBI PMU Team |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*