

Fortnightly Progress Report

SIDBI – PMU Maharashtra

Period – 1st to 15th February, 2023

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Maharashtra**  **Month & Year: February 2023**  **Fortnight Ending: 15th February, 2023** | **Report Summary**  This Report includes the activities carried out by SIDBI - PMU for development of MSME Ecosystem in the State of Maharashtra. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | Consultant | Abhay Ravetkar | 5th April, 2021 |
| 2 | Business Analyst | Shital Shintre | 10th Oct, 2022 |

**Details of State Nodal Connect - Name– Devraj Madam, Superintendent Industry Officer) – 08425887836**

**Activities performed by PMU during fortnight ending 15th February 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| **General Activities to facilitate project implementation** | |
| 1.SCDF –  Skill & FD Department:   * Follow up by PMU team with officials of Skill Development department was done because of this the file of Panvel ITI up-gradation project was submitted to Finance Department with due approval of senior officials of Skill Dev. Dept. * -The DPR prepared was also put up for approval of Skill development dept. IT was primarily approved with few suggestions in it. It was also sent to Finance department for their review. Upon review it will be sent to SIDBI as an application/proposal for fund under SCDF. * PMU team facilitated SIDBI & FD to arrange meeting with MS. Shaila, Principal Secretary on 14th Feb 2023 for discussing the MoU terms & signing formalities. Detailed Discussion held during the meeting SIDBI Central Team officials were present. It was decided that State Government will initiate the MOU singing Process shortly & will also check with other department whether, they have any proposal which can be eligible under SCDF. * The Draft MoU copy submitted by SIDBI to FD has been sent to Legal dept. of State Dept.     Energy Department –   * PMU Team met Mr. Badgeri, Under Secretary, Energy Dept. & discussed about the status Projects which they had identified & sent to SIDBI for their initial scrutiny whether said projects are eligible for SCDF. Mr. Badgeri enquired about possibility of various kinds of Energy projects to get eligibility under SCDF. * Based on discussion, PMU team has been asked visit to MSEDCL & discuss about the projects, that will be sent to SIDBI & FD, also asked to check whether, FD will take loan given to MSEDCL under their books of Accounts. * MSEDCL officials has written letter to Principal Secretary, Energy Department regarding the ongoing update on SCDF fund. * PWD-Roads: PMU team met Mr. Kachare, Under Secretary to enquire about status of PWD project proposals costing about Rs. 7000. Cr., that have been selected & approved by them & sent to FD., It was understood that the file of proposals is with planning dept. for budgeting. * As per suggestion of Under Secretary, PMU team met Mr. Manoj Sainik, ACS, Finance & PWD & discussed possibility of various projects that can be taken under SCDF. | |
| 4. PMU team facilitated a meeting of CGTMSE & SIDBI officials with Hon’ble Principal Secretary, Dept. of Ind. & Commerce. | |
| 5. Assistance to Dept. of Industries in making arrangement for Industrial Investments Summit programme to be conducted in Maharashtra, prepared a letter requesting SIDBI for their participation. | |
| 6. ONDC.   * Follow up with ONDC officials for providing details for initiating a ONDC Engagement, processed, Primary brief was given to Dev. Commissioned & SIO regarding ONDC. * Follow up with ONDC officials to have online capacity building session of Industry & related officials about ONDC & Product on boarding process on ONDC. * Enquiry with Nandurbar DIC officials regarding ONDC related activities carried out in District | |

|  |
| --- |
| **Activities Way forward** |
| 1. Support ONDC for singing of MoU with GOM 2. Liasoning with Rajasthan NGO for capacity building of Maharashtra Cluster Units for designing. 3. SCDF MoU with Finance Department 4. State CGTMSE for CMEGP & Clusters |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*