

Fortnightly Progress Report

SIDBI – PMU Maharashtra

Period – 1st to 15th March 2023

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Maharashtra**  **Month & Year: March 2023**  **Fortnight Ending: 15th March, 2023** | **Report Summary**  This report includes the activities conducted by SIDBI - PMU for the  facilitation of MSME Ecosystem in the State of Maharashtra. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | Consultant | Abhay Ravetkar | 5th April, 2021 (In Maharashtra PMU 4th Feb- 2023) |
| 2 | Business Analyst | Shital Shintre | 10th Oct 2022 |

**Details of State Nodal Connect - Name – Devraj Madam – 08425887836 (SIO)**

**Activities performed by PMU during fortnight ending 15th March 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| **General Activities to facilitate project implementation** | |
| 1.SCDF –  **Skill Department**: PMU is in continuous touch and meeting various stakeholders in Skill Department for moving the file. With the current status first DPR and file of Panvel ITI is being approved by Finance and sent back to Skill Department. Skill Department will now be sending the budgetary requirement and request for loan under SCDF to Finance. PMU is following up with the Department to move the file to Finance and post which the Finance Department will be signing the master agreement. Skill Department are arranging the meeting with Finance and SIDBI on 25th January 2023 regarding SCDF.PMU is in touch with Finance Department and have meet Secretary Finance and JS Finance at various level along with DGM SIDBI to explain about SCDF and agree on Master Agreement.  The MoU copy of SCDF was sent by legal department to Finance department with their remarks on it, the remark was, approval of Finance department Authority to be taken & GR to be drafted & execute, PMU team prepared a note of SCDF guideline in Marathi Language & submitted to FD. Follow up is being made to finalise the GR.  **Energy Department** – PMU had meeting with MSEDCL Director and Finance team along with EDI senior officials, Director Finance communicated that they need lot of funds but are unsure about the process of the SCDF as Finance Department won’t be taking the loan on their books. With the last meeting held, MSEDCL officials will be writing letter to P Sec Energy Department regarding the ongoing update on SCDF fund. Post this letter there will be more clarity. Follow up is being made.  **PWD-Roads**: PMU held various meetings few of them was along with SIDBI GM with Secretary PWD regarding the selection of projects. PWD department has selected 1000 cr proposal and are being approved by Minister to avail SCDF fund. This file will be sent to Finance & Planning on the list of new projects. PMU have meet the Secretary PWD now file is move to PWD department and singed by secretary of PWD then send by Finance department. PMU is following up with the department to move the file as soon as possible. | |
| 2. Green Finance – Follow up is on to take CFC projects under MSE-CDP & MSI -CDP to be taken under SIDBI green financing Scheme, also held discussion whether MNRE department scheme can also to be implemented for the same. | |
| 3. As directed by JDI PMU team is doing secondary research of Coir policies of State & Central government to identify potential for Maharashtra state to develop & restructure existing policy ort programme. | |
| 4. PMU team is studying Handicraft & Handloom policy of other State to compare & identify the Gap in Handicraft & Handloom policy of Maharashtra. | |
| 5. Submitted a copy of SCDF English translated Scheme Document to Skill Department for drafting the GR | |
| 6. PMU team coordinated with Miss. Uma Devi, promoter of Rajasthan State “Chalisgaon” women’s cluster for assisting Maharashtra garment cluster members to develop new designed idea/s in garment sector in Maharashtra | |
| 9. As directed by JDI, PMU team helped the department in drafting the letter to CGTMSE to implement it for SCFS from Maharashtra. | |

|  |
| --- |
| **Activities way forward** |
| 1. State CGTMSE 2. Study & comparison of Coir, Handloom & handicraft Policy. 3. MOU with State Government for SCDF. |
| **Inputs of State Nodal Connect / Officer** |
| 1. Good work by SIDBI PMU Team |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*