

Two Month Progress Report

(Jan-Feb)2023

SIDBI – PMU Maharashtra

**Activities performed by PMU during January –February 2023**

1. **Policy Development Support**

* Maharashtra State is working in setting up a flatted gala policy and Submitted a draft concept Note on the components of Flatted gala policy and its framework, which is still work in progress and attract major investment in the sector.
* Department has also asked PMU to work and analyse on Handicraft and handloom policy and incentives mapping
* PMU help to the department for Industrial Investments Summit programme in Maharashtra and also prepaid a letter for SIDBI to join as Co-organizing institution
* PMU has Supported the cluster department to Prepaid the PPT for new guidelines of MSC-CDP for Chief Secretary meeting

1. **Enhancing Credit Flow to MSMEs**

* PMU has facilitated the ONDC introduction and context setting to new Development Commissioner and has planned the road map on how to leverage the benefits of the ONDC

1. **Strengthening Infrastructure for MSMEs:**
2. **Convergence with GoI/ State Govt. Schemes**

* PMU also had a discussion with Department on increasing the SFURTI clusters and identified a Kolhapuri SFURTI cluster. PMU had discussion with Kolhapuri chappal stakeholders and sensitized the scheme. PMU held meeting with Department and have identified the list of clusters which are not fitting in state cluster scheme.
* PMU Discuss the department about RAMP Scheme and submitted the one concept note and attended the meeting with Board of Directors of RAMP committed to declared the SIP of the RAMP Scheme.
* PMU also facilitated the SIDBI’s Green Initiative schemes and trying to explore the various activities which State MSMEs can get benefited of.

1. **Institutional Strengthening of MSME Stakeholders**

* PMU arranged the meeting with Hon’ble Principal Secretary, Industries and SIDBI for CGTMSE and brief was given CGTMSE official proposed State Govt.
* PMU and SIDBI GM briefed members about SIDBI Venture Capital Fund Scheme, which is very excellent option for MSMEs.

1. **Entrepreneurship Development & Employment**

* PMU ideated the concept on skilling of selected clusters on pilot basis wherein SIDBI along with Industries Department will be arranging a training program to fill the skill gaps at ground level, which will address the skilling challenges which clusters are facing. Have also prepared a draft concept note and is under review by Department. PMU is exploring for a scope for interventions on skilling of clusters and having rounds of meetings with the department if a proposal can be worked out to SIDBI for the same.

1. **SCDF related Interventions**

* Skill Department: PMU is in continuous touch and meeting various stakeholders in Skill Department for moving the file. With the current status first DPR and file of Panvel ITI is being approved by Finance and sent back to Skill Department. Skill Department will now be sending the budgetary requirement and request for loan under SCDF to Finance. PMU is following up with the Department to move the file to Finance and post which the Finance Department will be signing the master agreement. In 14th February 2023 the meeting was done with Finance Department in this meeting finance Department raise query now they clear all there query now the Department has ready to signing the Agreement within few days. Same day the Principal Secretary Miss Shaila madam held meeting with various department and give the suggestion to all department take a SIDBI loan. Now the Panvel ITI file send to legal department
* Energy Department – PMU had meeting with MSEDCL Director and Finance team along with EDI senior officials, Director Finance communicated that they need lot of funds but are unsure about the process of the SCDF as Finance Department won’t be taking the loan on their books. With the last meeting held, MSEDCL officials will be writing letter to P Sec Energy Department regarding the on going update on SCDF fund. Post this letter there will be more clarity. PMU also planned to meet MSEDCL Director (Finance) this week.
* PWD-Roads: PMU held various meetings few of them was along with SIDBI GM with Secretary PWD regarding the selection of projects. PWD department has selected 1000 cr proposal and are being approved by Minister to avail SCDF fund. This file will be sent to Finance & Planning on the list of new projects. PMU have meet the Secretary PWD now file is move to PWD department and singed by secretary of PWD then send by Finance department. PMU is following up with the department to move the file as soon as possible.

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*