

One Month Progress Report

(December)2022

SIDBI – PMU Punjab

**Activities performed by PMU during October- November 2022**

1. **Policy Support to State:**
2. After analysing the need of SIP in state and in-depth discussions with Joint Director, DI&C Punjab, The PMU developed & submitted RFP on SIP Under RAMP Scheme.
3. Submitted Template 1 & 2 for Second National Chief Secretary Conference Under Vikshit Bharat to department by assessing suggestion received from Industry stakeholders.
4. Prepared a draft benchmarking document on Mini Cluster Development Schemes developed by different states.
5. Verified data of Industry association through updating their current status of Presence in Industry. PMU Team Planning to develop a mechanism for easily access of data through digital mode.
6. **Convergence - Strengthening infrastructure for MSME through State scheme / twinning with GoI schemes:**
7. Participated in National Workshop with States on Preparation of SIP under RAMP dated 20/10/2022 where SIDBI PMU team had developed RFP on SIP for State.
8. Under MSE-CDP PMU identified a Kinnow Cluster at Fazilka district. PMU Providing Support to GM, DIC for Preparing Plan to cover the Proposal Under GoI Scheme.
9. Prepared & Submitted note on SFURTI Proposal for a Workshop on SFURTI Scheme for industry department.
10. Participated in Awareness Generation Workshop on TReDS for MSME under RAMP Programme Conducted by Ministry of MSME, Government of India.
11. **Institutional Strengthening & Capacity Building of stakeholders:**
12. Prepared & Submitted note on TReDS Workshop Proposal for Commerce department. PMU team is in Discussion with all three RXIL, M1 Exchange, Invoice Mart for a Physical session, to facilitating the department on TReDS Platform.
13. For creating Awareness among industry Stakeholders on Punjab Government Policy, SIDBI Schemes & Government of India Schemes, PMU has developed an Institutional Mechanism where all the districts of Punjab get aware about Schemes & policy. An Awareness programme is going to held in this regard on dated 02/12/22 at Mohali (S.A.S Nagar) District.
14. **SCDF related intervention:**
15. Meeting held withPSIDC to appraise the scheme andsuggested potential projects for the scheme.
16. Followed up with Finance department for next round meeting with PS, Finance. Followed up with PEDA, Tourism department for potential projects.
17. Meeting held with the chief engineer, PSIDC and appraised him about the SCDF. PMU will help in identifying Potential Project.
18. Appraised the official of Punjab State Transmission Corporation Limited (PSTCL) on SCDF and facilitated him to identify the relevant project.

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*