

Fortnightly Report

SIDBI – PMU Bihar

Period – 01st April 2023- 16th April 2023

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Patna**  **Month & Year: April 2023**  **Fortnight Ending: 30st April 2023** | **Report Summary**  This Report includes the activities carried out by SIDBI - PMU for the  facilitation of MSME Ecosystem in the State of Bihar |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **S. No.** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | PMU Manager | Ravi Kant Bharti | 16-January-2023 |
| 2 | Business Analyst | Preeti Shree | 16-August-2022 |
| 3 | Business Analyst | Vikas Bhardwaj | 03rd April 2023 (Replacement of Preeti Shree) |

**Details of State Nodal Connect –**

**From SIDBI –** Mr. Pradeep Jha, SIDBI

**From Industries, GoB:** Mr. Pankaj Dixit, Director Industries

**Activities performed by PMU during 01st April – 16th April 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of Activities carried out** |
| **Activities against Action Plan** | |
| 1. MSE-CDP- After submission of Final Appraisals Copy on Portal, MSME’s local office has been given the portal for GIS Mapping to submit the final copy to Central Office of MSME. Facilitate and support to Local MSME’s Officials to Spot GIS mapping for 9 MSE-CDP proposed site and submitted all 09 proposal to Central Office of MSME. 2. 2 MSE-CDP proposal has been submitted to SIDBI for Technical appraisal, query has been raised and support to DOI to resolve the query. 3. Prepare the ToR for Young Professional recruitment and submitted to Director- Industry. After receiving the suggestion and instruction, another draft copy to ToR has been submitted to Director- Industry. 4. MSME- International Cooperation Events- Meeting conducted by DI with MSME team, EPCH. There is various event organised by MSME where entrepreneurs could participate in Bihar as well as outside. Under various scheme PMU supporting in those potential units for end-to-end participation. We have shared the event calendar and coordinating with sectors.   **Others**   * Designed ranking format for IEOs and data preparation. * DIC Ranking sheet and PPT preparation. * PMU Bihar facilitated the DOI for SLBC meeting with data, documents and support required. * Department scheme PPTs (MSME, MSE-CDP, ZED, SFURTI and DOI Schemes) for Monthly meeting. * PMEGP-Bank & District wise data preparation * Support to Department for MSE-FC meeting and prepared the legal order and related matters.   Way Forward:   * MSME events coordination continues * ZED Registration * SIDBI-SRLM collaboration indicator | |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the Project Management Unit. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*