

Fortnightly Report

SIDBI – PMU Bihar

Period – 16th January 2023- 31st January 2023

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Patna**  **Month & Year: January 2023**  **Fortnight Ending: 31st January 2023** | **Report Summary**  This Report includes the activities carried out by SIDBI - PMU for the  facilitation of MSME Ecosystem in the State of Bihar |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **S. No.** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | PMU Manager | Ravi Kant Bharti | 1-January-2023 |
| 2 | Business Analyst | Preeti Shree | 16-August-2022 |

**Details of State Nodal Connect –**

**From SIDBI –** Mr. Pradeep Jha, SIDBI

**From Industries, GoB:** Mr. Pankaj Dixit, Director Industries

**Activities performed by PMU during 16th January – 31st January 2023**

|  |
| --- |
| **Activities against Action Plan** |
| **Strengthening Infrastructure for MSME**   * Appraisals from SIDBI and SLCC meeting also completed. Coordination with SIDBI for receiving the final copy so, that it could be uploaded by PMU to complete the procedure. * Working on proposals for CFC projects (textile & metal clusters) with DOI and scoping it with SIDBI where working capital support could be a visible indicator.   **Convergence**   * SFURTI- Coordinated and completed the 2nd round of meeting with Director Industries, Director Handloom and Director KVIC for finalising the technical agency. NIFT Kolkata has been selected as Technical Agency and coordinating for further preparation of DPRs for 3 concept proposals. * One new concept proposal (Rohtas-Blanket) has been prepared and submitted under SFURTI. * Coordinating with KVIC and academic institutes for empanelment in SFURTI Technical agency. * PMU coordinating for verification of artisan’s data and cluster under SFURTI for Gaya, Bhagalpur, and Patna. * RAMP- SIP document go through and drawing major points to work upon. * Mapping of SNA-CNA, coordinating for end-to-end results   **Entrepreneurship Development and Employment Generation**   * Supporting and Liasoning with Start-up team (DOI) for MOU between SIDBI and DOI for Start-up funding (AIF). In this regard a meeting with start-up team has been done and trying to get it done through DOI in next coming weeks. Final draft also processed through file for approval.   **Institutional Strengthening & Capacity Building of Stakeholders**   * Implementing ZED scheme with benefits in the industrial policy- discussion with the central team and proposed to industries so that we could work on draft.   **Others**   * Supporting DOI on a report where impact could be seen through policies and data. * DIC ranking data and presentation prepared by PMU * PMEGP-Bank & District wise data preparation * PMEGP/PMFME bank wise data preparation for review. * Chief Secretary review data and ppt presentation. |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the Project Management Unit. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*