

Fortnightly Report

SIDBI – PMU Bihar

Period – 1st December 2022- 15th December 2022

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Patna**  **Month & Year: December 2022**  **Fortnight Ending: 31st December 2022** | **Report Summary**  This Report includes the activities carried out by SIDBI - PMU for the  facilitation of MSME Ecosystem in the State of Bihar |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **S. No.** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | PMU Manager | Swati Singh | 1-June-2022 |
| 2 | Business Analyst | Preeti Shree | 16-August-2022 |

**Details of State Nodal Connect –**

**From SIDBI -** Mr. Pradeep Jha, Branch Manager, SIDBI

**From Industries, GoB:** Mr. Pankaj Dixit, Director Industries

**Activities performed by PMU during 1st December – 15th December 2022**

|  |
| --- |
| **Activities against Action Plan** |
| **Improved Governance Framework/ Policy Advocacy**   * Prepared comparison sheet for different cluster-based schemes. Identified Cluster based schemes and going through the details to differentiate framework designed. Connecting schemes with most relevant scopes and implementation.   **Strengthening Infrastructure for MSME**   * PMU supported in a Food Processing convergence meeting with Agriculture, Horticulture, Comfed, Bihar-SRLM to boost the production of products such Litchi, Makhana, Mushroom and Honey. Coordination with the respective stakeholders. Preparation of data sheet for finding out the existing units in Bihar with their functionality and invested cost by coordinating and following up with districts.   **Enhancing Credit flow to MSMEs**   * Arrangement with NBFCs- Received the response from IIFL Samasta Finance Ltd for having another round of meeting to discuss further. However, 1st round of discussion already done with UP team so, waiting for the next communication to move ahead. Figuring out the possible ways to connect with Annapurna Finance, L&T Finance and Saija Finance. * Exploring the Green Financing/EV options in Bihar from SIDBI perspective. * Initial phase of discussion with Jeevika-SRLM to scope out the projects to work with SIDBI. 2nd round of meeting to be planned for figuring out the further ways.   **Convergence**   * SFURTI-Seven Concept Note prepared by PMU in coordination with Departments (Handloom & Handicraft) and submitted to the Nodal Agency. Following up with the Nodal Agency for further procedures. 4 more concept notes are in process to be prepared and uploaded.   Submitted proposals follow up and discussion with KVIC and Director-Industries.   * RAMP- PMU assisted in shortlisting applications and preparing data of applications received. Further coordinating for successful completion of recruitment process.   **Entrepreneurship Development and Employment Generation**   * Supported in the evaluation process of new 200 applications of start-ups under Bihar Start Up Policy 2022. * Supported in the Start-Up event planning at college campus for awareness. * Start-up support to department for finalising beneficiaries for next round of seed fund * Support in organising and coordinating Awareness camp for start-up/MSMEs in colleges * Coordination for start-up online examination * Start-Up seed fund tranche disbursement under New Bihar Start-Up Policy. * Interacted with Entrepreneurs related to textile for handhold support   **Others**   * DIC data and presentation prepared by PMU * 1 Case Studies prepared for Department of Industries. * MSME Review Meetings with PS and Director-Industries * SIDBI-Meeting with GM sir for detailing the deliverables and review. Also discussed the roadmap. |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the Project Management Unit. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*