

Fortnightly Report

SIDBI – PMU Punjab

Period – 1st To 15th December 2022

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Chandigarh**  **Month & Year: December 2022**  **Fortnight Ending: 15th December 2022** | **Report Summary**  This Report includes the activities carried out by SIDBI - PMU for the  Facilitation of MSME Ecosystem in the State of Punjab. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | PMU Manager | Sanjeev Chaudhary | 5th December 2022 |
| 2 | Business Analyst | Abhinav Parmar | 18th July 2022 |

**Details of State & SIDBI Chandigarh Connect –**

**Name – Mr. Vishav Bandhu, Joint Director, PI&C Mobile: 9814746156 Email:** [**piu.ibdp2017@gmail.com**](mailto:piu.ibdp2017@gmail.com) **and Mr. Himanshu Kumar, Manager, RO, Mobile: 9648565310, Email: himanshuj@sidbi.in**

**Activities performed by PMU during fortnight ending on 15th December 2022**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| **General Activities to facilitate project implementation** | |
| 1. **Policy Support to State-** Preparing MSME Profile for Punjab State. It will provide a brief idea about state Economic Status, Social culture and MSME ecosystem in the state. | |
| 1. **Institutional Strengthening & Capacity Building of stakeholders**- Organized Awareness Programme on SIDBI & Government of India Schemes for MSMEs at Mohali district. 100+ MSMEs attended the program.   Prepared & Submitted SIDBI Compendium of Schemes to Commerce Dept. (Annex 1). | |
| 1. **Enhancing credit flow to the MSME Sector and Cluster financing –** Arranged list of major Industries onboarded on RXIL Platform under TReDS. Assessing data and coordinating with sellers to onboard on RXIL Platform. (Annex 2) | |
| 1. **Convergence - Strengthening infrastructure for MSME through State scheme-** Identified Potential Cluster under Mini Cluster Development Scheme in Haryana for Exposure Visit of MSMEs and Govt officials. The visit will Provide insights on working mechanism of CFC. (Annex 3) | |
| 1. **Partnership of State Govts & State level Industry-** Meeting held with official of Amazon on queries raised by dept. for onboarding of Product,Preparing Proposal for Promoting E-commerce. | |
|  | |

|  |
| --- |
| **Actionable and Support required** |
| 1. Dates for Exposure visit to be finalised after discussion with Stakeholders. |
| **Activities Way forward** |
| 1. Exposure visit of Haryana State Mini Cluster Development Projects in Jan & Feb 2023. 2. Compendium of SIDBI Schemes will be uploaded in Invest Punjab Portal. 3. State MSME Profile will be submitted to Department as well as SIDBI. |
| **Inputs of State Nodal Connect / Officer** |
| 1. |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*