

FortnightlyReport

SIDBI – PMU Madhya Pradesh

**Period–1st– 15th February 2023**

**Project Progress Report–Fortnightly**

|  |  |
| --- | --- |
| **SIDBI MP State PMU for MSME** | |
| **Location: Bhopal**  **Month & Year: February 2023**  **Fortnight Ending: 15th February 2023** | **ReportSummary**  This report includes the activities carried out bySIDBI-PMU fort he  Facilitation of MSM Ecosystem in the State of Madhya Pradesh. |

**TeamDeploymentStatus**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Nameof Resource** | **DeploymentDate** |
| 1 | PMUManager | Binu Chaturvedi | 9th Jan 2023 |
| 2 | BusinessAnalyst | Mohammed Zafar | 9th Jan 2023 |

**Details of State Nodal Connect - Name – Shri Pankaj Dubey, Dy.Director,Department of MSME, Mobile: 9179831101, Email:** [pankaj.dubey25@mp.gov.in](mailto:pankaj.dubey25@mp.gov.in)

**Activities performed by PMU during fortnight ending January 31, 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| 1. **Prepared and submitted concept note on MPLUN (Annex 1)**  * In compliance to the directions, PMU has interreacted with MPLUN ,MSME and MPIDC officers and stakeholders to assess the strength, gaps and KRAs of the MPLUN and expectation of the MSME department. Under the mentioned arrangement with SIDBI Department of MSME GoMP expressed their concern w.r.t. strengthening of Madhya Pradesh Laghu Udyog Nigam also kwon MPLUN. In an inception meeting with SIDBI PMU MP Team, Secretary MSME, GoMP. Directed Grant Thornton (SIDBI PMU MP) to undertake strengthening of MPLUN as exclusive PSU for MSME Department. | |
| 1. **Presentation on MPIDC (Annex 2)**  * As suggested by Director of Industries GoMP, PMU team prepared and submitted presentation on MPIDC to understand the revenue model, scope of work, structure of MPIDC | |
| 1. **Training cum orientation program on PMU Tracker**  * PMU team organised 2 training and orientation programs for SIDBI, under which session on process flow, PMU tracker manual were discussed. Team GT & SIDBI attended the program respectively. | |
| 1. **TReDS**  * PMU Team facilitated a virtual meeting between MSME Department, GoMP and RXIL officers | |
| 1. **State CGTMSE scheme**  * PMU is supported department of MSME to prepare state CGTMSE scheme, under which one virtual meeting was conducted between CGTMSE and Secretary Industries GoMP. | |
| 1. **ODOP in UP (Annex 3)**  * As suggested by director of industries, PMU prepared and submitted presentation on one district and one product from Uttar Pradesh | |
| 1. **SCDF**  * PMU Team facilitated series of meeting for Shri, Javed Siddiqui, DGM, SIDBI with Secretary, MSME, MD MPIDC, Director Budget, GoMP to promote SCDF in the State. * State Government asked SIDBI to propose a meeting with Honorable CM and CS w.r.t. SCDF | |

|  |
| --- |
| **ActionableandSupportrequired** |
| * To provide guidance and support in the implementation of various activities of the project |
| **ActivitiesWayforward** |
| * To Explore potential departments of GoMP having requirement of SCDF * To conduct one day orientation program for District level MSME officers (GM DTICs) |
| **InputsofState NodalConnect/Officer** |
| 1. Strengthening of MPLUN |

**Contactus**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices asmentionedbelow:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEWDELHI**  National Office,Outer Circle, L 41,Connaught Circus,New Delhi - 110001T+911142787070 | **NEWDELHI**  6thFloor,Worldmark2,Aerocity,  New Delhi - 110037T+911149527400 | **AHMEDABAD**  7thFloor,HeritageChambers,  Nr Azad Society,Nehru Nagar,Ahmedabad-380015 | **BENGALURU**  5thFloor,65/2,BlockA,Bagmane Tridib,Bagmane Tech Park,CV Raman Nagar,Bengaluru-560093  T+918042430700 | **CHANDIGARH**  B-406A, 4th Floor, L&TElante Office Building,IndustrialAreaPhaseI,Chandigarh -160002  T+911724338000 |
| **CHENNAI**  7thFloor,PrestigePolygon,  471, Anna Salai,Teynampet,Chennai-600018  T+914442940000 | **DEHRADUN**  SuiteNo2211,2ndFloor,Building 2000, MichiganAvenue, Doon ExpressBusiness Park,  Subhash Nagar,Dehradun-248002  T+911352646500 | **GURGAON**  21stFloor,DLFSquare,Jacaranda Marg, DLFPhaseII,  Gurgaon- 122002  T+911244628000 | **HYDERABAD**  7th Floor,BlockIII,WhiteHouse,  Kundan Bagh,Begumpet,Hyderabad-500016  T+914066308200 | **KOCH**I  6thFloor,ModayilCentrePoint, Warriam RoadJunction, MGRoadKochi-682016  T+914844064541 |
| **KOLKATA**  10CHungerfordStreet,5th Floor,  Kolkata-700017  T+913340508000 | **MUMBAI**  11thFloor,TowerII,  One International Center,SB Marg Prabhadevi (W),Mumbai-400013  T+912266262600 | **MUMBAI**  Kaledonia,1stFloor,C Wing, (OppositeJ&J Office),  Sahar Road,AndheriEast,  Mumbai-400 069 | **NOIDA**  PlotNo19A,2ndFloor,Sector-16A,  Noida-201301  T+911204855900 | **PUNE**  3rdFloor,UnitNo309-312, West Wing, NyatiUnitree, Nagar Road,Yerwada  Pune-411006  T+912067448800 |

Formoreinformationorforanyqueries,writetousat[**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Followus@GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts asthe Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and MediumEnterprise(MSME)sectoraswellasforco-ordinationoffunctionsofinstitutionsengagedinsimilaractivities.Inthecontext of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBIVision2.0whichenvisagesanintegratedcreditanddevelopmentsupportroleoftheBankbybeingathoughtleader,adoptingacredit-plusapproach,creating amultipliereffectand servingasanaggregatorinMSMEspace.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementingagency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any actiontakenbyitbasedonthisdocument.SIDBI,itsdirectors,employeesoranyofficeshallnotbeliableforlossofwhatsoevernaturearising byusingthecontentofthisdocument.*