

FortnightlyReport

SIDBI – PMU Madhya Pradesh

**Period– 1st to 15th March 2023**

**Project Progress Report–Fortnightly**

|  |  |
| --- | --- |
| **SIDBI MP State PMU for MSME** | |
| **Location: Bhopal (MP)**  **Month & Year: March 2023**  **Fortnight Ending: 15th March 2023** | **ReportSummary**  This report includes the activities carried out by SIDBI-PMU for the  Facilitation of MSM Ecosystem in the State of Madhya Pradesh. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Nameof Resource** | **DeploymentDate** |
| 1 | PMU Manager | Binu Chaturvedi | 9th Jan 2023 |
| 2 | Business Analyst | Mohammed Zafar | 9th Jan 2023 |

**Details of State Nodal Connect - Name – Shri Pankaj Dubey, Dy.Director,Department of MSME, Mobile: 9179831101, Email:** [pankaj.dubey25@mp.gov.in](mailto:pankaj.dubey25@mp.gov.in)

**Activities performed by PMU during fortnight ending March 15, 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| 1. **Joint Consultation meeting with MPLUN Head of Department**  * In compliance to the directions by Director Industries, PMU had made a presentation to all the head of department of MPLUN on progress made for strengthening of MPLUN. PMU highlighted the gap and projected necessary steps to overcome it. | |
| 1. **Financial analysis of MPLUN**  * PMU conducted detailed financial analysis of last 5 years performance of MPLUN | |
| 1. **Consultation meeting with HR expert**  * PMU had series of detailed discussion with HR expert Shri. Ravi Mathur to prepare revised HR set-up for MPLUN | |
| 1. **Concept Note on one day training program of GM DTICs**  * PMU team prepared concept note and detailed agenda for organizing one day training cum orientation program of GM DTICs and supporting staff on cluster development, preparation of DSR and DPR etc. | |
| 1. **PMU Tracker**  * Under maintenance and updating of PMU tracker following issues were resolved by PMU- * SIDBI officials (verifier/approver) not mapped (Rajasthan) * SIDBI verifier/approver not able to do their task (UP, Delhi etc) * Old test file uploaded still exists. * Creation of Login ID for all SIDBI State/RO office. | |
| 1. **State CGTMSE Scheme**  * PMU team in consultation with Department of MSME coordinated with CGTMSE team. Therefore, a physical meeting is organised with CGTMSE in coming weeks | |
| 1. **Meeting with MD MP Agro and Institutional Finance**  * Follow up with MD MP Agro and DIF regarding loan under SCDF | |
| 1. **SCDF-**  * Multiple discussion held with skill development department, MP Agro and Department of MSME for SCDF | |

|  |
| --- |
| **Actionable and Support required** |
| * To provide guidance and support in the implementation of various activities as per action plan |
| **ActivitiesWayforward** |
| * To Explore potential departments of Go MP having requirement of SCDF * Strengthening of DTICs * Strengthening of MPLUN as an exclusive corporation of MSME department * To conduct one day orientation program for District level MSME officers (GM DTICs) * CGTMS orientation |
| **Inputs of State Nodal Connect/Officer** |
| 1. Strengthening of MPLUN 2. On various planed activities for implementation |

**Snapshot of performed activities-**

|  |  |
| --- | --- |
| Figure PMU Manager Shri. Binu Chaturvedi giving presentation on MPLUN | Figure 2 PMU Manager Shri. Binu Chaturvedi giving presentation on MPLUN |

**Contactus**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices asmentionedbelow:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEWDELHI**  National Office,Outer Circle, L 41,Connaught Circus,New Delhi - 110001T+911142787070 | **NEWDELHI**  6thFloor,Worldmark2,Aerocity,  New Delhi - 110037T+911149527400 | **AHMEDABAD**  7thFloor,HeritageChambers,  Nr Azad Society,Nehru Nagar,Ahmedabad-380015 | **BENGALURU**  5thFloor,65/2,BlockA,Bagmane Tridib,Bagmane Tech Park,CV Raman Nagar,Bengaluru-560093  T+918042430700 | **CHANDIGARH**  B-406A, 4th Floor, L&TElante Office Building,IndustrialAreaPhaseI,Chandigarh -160002  T+911724338000 |
| **CHENNAI**  7thFloor,PrestigePolygon,  471, Anna Salai,Teynampet,Chennai-600018  T+914442940000 | **DEHRADUN**  SuiteNo2211,2ndFloor,Building 2000, MichiganAvenue, Doon ExpressBusiness Park,  Subhash Nagar,Dehradun-248002  T+911352646500 | **GURGAON**  21stFloor,DLFSquare,Jacaranda Marg, DLFPhaseII,  Gurgaon- 122002  T+911244628000 | **HYDERABAD**  7th Floor,BlockIII,WhiteHouse,  Kundan Bagh,Begumpet,Hyderabad-500016  T+914066308200 | **KOCH**I  6thFloor,ModayilCentrePoint, Warriam RoadJunction, MGRoadKochi-682016  T+914844064541 |
| **KOLKATA**  10CHungerfordStreet,5th Floor,  Kolkata-700017  T+913340508000 | **MUMBAI**  11thFloor,TowerII,  One International Center,SB Marg Prabhadevi (W),Mumbai-400013  T+912266262600 | **MUMBAI**  Kaledonia,1stFloor,C Wing, (OppositeJ&J Office),  Sahar Road,AndheriEast,  Mumbai-400 069 | **NOIDA**  PlotNo19A,2ndFloor,Sector-16A,  Noida-201301  T+911204855900 | **PUNE**  3rdFloor,UnitNo309-312, West Wing, NyatiUnitree, Nagar Road,Yerwada  Pune-411006  T+912067448800 |

Formoreinformationorforanyqueries,writetousat[**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Followus@GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts asthe Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and MediumEnterprise(MSME)sectoraswellasforco-ordinationoffunctionsofinstitutionsengagedinsimilaractivities.Inthecontext of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBIVision2.0whichenvisagesanintegratedcreditanddevelopmentsupportroleoftheBankbybeingathoughtleader,adoptingacredit-plusapproach,creating amultipliereffectand servingasanaggregatorinMSMEspace.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementingagency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any actiontakenbyitbasedonthisdocument.SIDBI,itsdirectors,employeesoranyofficeshallnotbeliableforlossofwhatsoevernaturearising byusingthecontentofthisdocument.*