

FortnightlyReport

SIDBI – PMU Madhya Pradesh

**Period–1st to 15th April 2023**

**Project Progress Report–Fortnightly**

|  |  |
| --- | --- |
| **SIDBI MP State PMU for MSME** | |
| **Location: Bhopal (MP)**  **Month & Year: April 2023**  **Fortnight Ending: 15th April 2023** | **ReportSummary**  This report includes the activities carried out by SIDBI-PMU for the  Facilitation of MSM Ecosystem in the State of Madhya Pradesh. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Nameof Resource** | **DeploymentDate** |
| 1 | PMU Manager | Binu Chaturvedi | 9th Jan 2023 |
| 2 | Business Analyst | Mohammed Zafar | 9th Jan 2023 |

**Details of State Nodal Connect - Name – Shri Pankaj Dubey, Dy.Director,Department of MSME, Mobile: 9179831101, Email:** [pankaj.dubey25@mp.gov.in](mailto:pankaj.dubey25@mp.gov.in)

**Activities performed by PMU during fortnight ending April 31, 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| 1. **Annual Action Plan (Annexure 1)**  * In compliance to the directions give in the inception meeting held on 17th Jan 2023 subsequently on 24th March 2023, the proposed action plan was discussed in a meeting led by Director MSME in the presence of other concerned officers of the directorate. * The action plan for the year 2023 incorporates further activities as suggested and in line with the terms of MOU | |
| 1. **SCDF workshop in Goa**  * PMU team had mobilized finance department and MSME department to participate in one day workshop on SCDF in Goa. Two officials from MSME Department was likely to participate in the schedule workshop | |
| 1. **Presentation for Strengthening of MPLUN as an exclusive corporation (Annexure 2)**  * In compliance to the directions ,to work out a strategic plan for strengthening of MPLUN, as an exclusive corporation for the MSME department. * PMU Team after series of consultations with concern stakeholders, and incorporating their views, submitted a strategic plan for strengthening of MPLUN is developed | |
| 1. **Concept Note on one day training program of GM DTICs**  * PMU team prepared concept note and detailed agenda for organizing one day training cum orientation program of GM DTICs and supporting staff on cluster development, preparation of DSR and DPR etc. | |
| 1. **SCDF**  * Discussion held with MSME officers about SCDF for cluster development | |

|  |
| --- |
| **Actionable and Support required** |
| * SIDBI may be requested to arrange training session on TReDS, SCDF, Direct finance schemes, Green Finance Scheme to MSME officials |
| **Activities Way forward** |
| * To Explore potential departments of Go MP having requirement of SCDF * Strengthening of DTICs * Strengthening of MPLUN as an exclusive corporation of MSME department * To conduct one day orientation program for District level MSME officers (GM DTICs) * CGTMS orientation |
| **Inputs of State Nodal Connect/Officer** |
| 1. Strengthening of MPLUN 2. On various planed activities for implementation |

**Contactus**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices asmentionedbelow:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEWDELHI**  National Office,Outer Circle, L 41,Connaught Circus,New Delhi - 110001T+911142787070 | **NEWDELHI**  6thFloor,Worldmark2,Aerocity,  New Delhi - 110037T+911149527400 | **AHMEDABAD**  7thFloor,HeritageChambers,  Nr Azad Society,Nehru Nagar,Ahmedabad-380015 | **BENGALURU**  5thFloor,65/2,BlockA,Bagmane Tridib,Bagmane Tech Park,CV Raman Nagar,Bengaluru-560093  T+918042430700 | **CHANDIGARH**  B-406A, 4th Floor, L&TElante Office Building,IndustrialAreaPhaseI,Chandigarh -160002  T+911724338000 |
| **CHENNAI**  7thFloor,PrestigePolygon,  471, Anna Salai,Teynampet,Chennai-600018  T+914442940000 | **DEHRADUN**  SuiteNo2211,2ndFloor,Building 2000, MichiganAvenue, Doon ExpressBusiness Park,  Subhash Nagar,Dehradun-248002  T+911352646500 | **GURGAON**  21stFloor,DLFSquare,Jacaranda Marg, DLFPhaseII,  Gurgaon- 122002  T+911244628000 | **HYDERABAD**  7th Floor,BlockIII,WhiteHouse,  Kundan Bagh,Begumpet,Hyderabad-500016  T+914066308200 | **KOCH**I  6thFloor,ModayilCentrePoint, Warriam RoadJunction, MGRoadKochi-682016  T+914844064541 |
| **KOLKATA**  10CHungerfordStreet,5th Floor,  Kolkata-700017  T+913340508000 | **MUMBAI**  11thFloor,TowerII,  One International Center,SB Marg Prabhadevi (W),Mumbai-400013  T+912266262600 | **MUMBAI**  Kaledonia,1stFloor,C Wing, (OppositeJ&J Office),  Sahar Road,AndheriEast,  Mumbai-400 069 | **NOIDA**  PlotNo19A,2ndFloor,Sector-16A,  Noida-201301  T+911204855900 | **PUNE**  3rdFloor,UnitNo309-312, West Wing, NyatiUnitree, Nagar Road,Yerwada  Pune-411006  T+912067448800 |

Formoreinformationorforanyqueries,writetousat[**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Followus@GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts asthe Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and MediumEnterprise(MSME)sectoraswellasforco-ordinationoffunctionsofinstitutionsengagedinsimilaractivities.Inthecontext of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBIVision2.0whichenvisagesanintegratedcreditanddevelopmentsupportroleoftheBankbybeingathoughtleader,adoptingacredit-plusapproach,creating amultipliereffectand servingasanaggregatorinMSMEspace.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementingagency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any actiontakenbyitbasedonthisdocument.SIDBI,itsdirectors,employeesoranyofficeshallnotbeliableforlossofwhatsoevernaturearising byusingthecontentofthisdocument.*