

Fortnightly Progress Report

SIDBI – PMU Chhattisgarh

Period – 16th to 31st December 2022

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Chhattisgarh**  **Month & Year: December 2022**  **Fortnight Ending: 31st December 2022** | **Report Summary**  This Report includes the activities carried out by SIDBI - PMU for the  facilitation of MSME Ecosystem in the State of Chhattisgarh. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | PMU Manager | Ishwar Kumar | 08th August 2022 |
| 2 | Business Analyst | Shubham Jha | 07th November, 2022 |

**Details of State Nodal Connect - Name – Shri Anil Tuteja (IAS), Director Industries, Chhattisgarh.**

**Shri Sanjay Gajghate, Joint Director Industries, Chhattisgarh.**

**Activities performed by PMU during fortnight ending 31st December 2022**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| 1. PMU team has conducted a training sessions for entrepreneurs regarding development of DPR for establishing an enterprise in the designated RIPA on 17th December 2022. The PMU has proposed for ToT for the Technical Support Agencies that will be appointed at district level for the development of RIPA. During interaction with SRLM, the PMU has proposed for signing an MoU between SRLM and SIDBI/FIs for bank linkage. | |
| 1. PMU has conducted a gap assessment for export preparedness and highlighted it to the DoI along with suggestions for developing an ERP for capturing such data on continuous basis. | |
| 1. In order to increase credit availability in the hands of MSMEs, the PMU team had submitted a proposal for Setting up of a state Venture Capital Fund with the support of SVCL to promote emerging start-ups in the state. In this regard, a presentation on the proposal was given by the PMU to the Secretary Industries. | |
| 1. PMU team approached the CGMFP Federation and have requested them to take up implementation of minor forest based cluster development under SFURTI Scheme. The discussions were positive and the Federation will submit 2 proposals regarding the same with the technical support of EDII Ahmedabad. | |
| 1. PMU team has completed a draft copy of (1) State MSME Profile, and (2) Compendium of Schemes for MSMEs in Chhattisgarh. After review, the copy will be submitted to DoI and SIDBI for consideration and suggestions. | |
| 1. PMU team has conducted cluster visits to Rice Cluster Dhamtari and Stone Cutting Cluster Mahasamund for green financing and cluster development under SFURTI. 20 units of Dhamtari Rice Cluster has shown interest for seeking finance for solar installation. | |
| 1. PMU has approached the trader associations in Raipur related to cloth, iron & steel, footwear, etc. and based on their demand the PMU approached the NRDA for taking up wholesale infrastructure development in Naya Raipur through SCDF. The meeting with CEO NRDA in likely to happen in mid-January, as she is away for training. | |
| 1. The PMU is regularly following up with DIF and secretary Finance for SCDF related approval. Based on demand from Finance Secretary, the PMU is working on 5 proposals submission under SCDF to the department. | |

|  |
| --- |
| **Actionable and Support required** |
|  |
| **Activities Way forward** |
| 1. Proposals for SIDBI SCDF fund and follow-up for Master Agreement Signing & Approval under Article 293 2. Stakeholder meeting is needed for cluster development 3. PMU to focus on cluster development activities through Central Govt. Schemes |
| **Inputs of State Nodal Connect / Officer** |
|  |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*