

FortnightlyReport

SIDBI – PMU Madhya Pradesh

**Period– 15th to 28th February 2023**

**Project Progress Report–Fortnightly**

|  |  |
| --- | --- |
| **SIDBI MP State PMU for MSME** | |
| **Location: Bhopal (MP)**  **Month & Year: February 2023**  **Fortnight Ending: 28th February 2023** | **ReportSummary**  This report includes the activities carried out by SIDBI-PMU for the  Facilitation of MSM Ecosystem in the State of Madhya Pradesh. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Nameof Resource** | **DeploymentDate** |
| 1 | PMU Manager | Binu Chaturvedi | 9th Jan 2023 |
| 2 | Business Analyst | Mohammed Zafar | 9th Jan 2023 |

**Details of State Nodal Connect - Name – Shri Pankaj Dubey, Dy.Director,Department of MSME, Mobile: 9179831101, Email:** [pankaj.dubey25@mp.gov.in](mailto:pankaj.dubey25@mp.gov.in)

**Activities performed by PMU during fortnight ending February 28, 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| 1. **Strengthening of MPLUN Presentation (Annexure 1)**  * In compliance to the directions, PMU had made a presentation to MD MPLUN on progress made for strengthening of MPLUN. MD MPLUN appreciated the presentation and suggest to have a detailed presentation to MPLUN senior officials in coming week. | |
| 1. **National Seminar on Procurement and Marketing support (Annex 2)**  * SIDBI-MSME PMU(GT) Represented SIDBI and Presented various schemes of SIDBI for MSMEs units in a National Seminar on Procurement and Marketing support organized by MSME development office of GoI held in Vidisha on 22 Feb 2023. PMU team apprised the house about the MOU executed between SIDBI- MSME department and the role of Grant Thornton. Other Govt agencies including NSIC, Export cooperation, BHEL,FIEO MSME department also presented their schemes for MSMEs | |
| 1. **Analysis of successful MSME PSUs of other States Government**  * Rapid analysis of successful model adopted by the MSME PSUs example- RICO, APIIC, GIDC, MPIDC, NSIC etc. Their best practices may be replicate by MP State MSME corporation. | |
| 1. **Meeting with MD of MP Agro and Director Institution Finance:** Meeting with Managing Director for SCDF, as department is planning to develop cluster for food processing and planning funds through SCDF for the machinery/equipment’s as per guidelines of SIDBI. | |
| 1. **SCDF**  * Director Budget, Finance department of Go MP suggested SIDBI to arrange a meeting with Chief Secretary and Hon Chief Minister for exploring various schemes of SIDBI and for SCDF that enable State Government to made budget provision well in advance | |

|  |
| --- |
| **ActionableandSupportrequired** |
| * To provide guidance and support in the implementation of various activities as per action plan |
| **ActivitiesWayforward** |
| * To Explore potential departments of Go MP having requirement of SCDF * Strengthening of DTICs * Strengthening of MPLUN as an exclusive corporation of MSME department * To conduct one day orientation program for District level MSME officers (GM DTICs) * CGTMS orientation |
| **InputsofState NodalConnect/Officer** |
| 1. Strengthening of MPLUN 2. On various planed activities for implementation |

**Snapshot of performed activities-**

|  |  |
| --- | --- |
| Figure 1 PMU Manager Shri. Binu Chaturvedi got felicitated by MSME DI Indore | Figure 2 Director of Industries, Shri. Rohit Singh, IAS |
| Figure 3 PMU Giving presentation on SIDBI schemes | Figure 4 National Seminar on Procurement and Marketing support (PMS) |

**Contactus**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices asmentionedbelow:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEWDELHI**  National Office,Outer Circle, L 41,Connaught Circus,New Delhi - 110001T+911142787070 | **NEWDELHI**  6thFloor,Worldmark2,Aerocity,  New Delhi - 110037T+911149527400 | **AHMEDABAD**  7thFloor,HeritageChambers,  Nr Azad Society,Nehru Nagar,Ahmedabad-380015 | **BENGALURU**  5thFloor,65/2,BlockA,Bagmane Tridib,Bagmane Tech Park,CV Raman Nagar,Bengaluru-560093  T+918042430700 | **CHANDIGARH**  B-406A, 4th Floor, L&TElante Office Building,IndustrialAreaPhaseI,Chandigarh -160002  T+911724338000 |
| **CHENNAI**  7thFloor,PrestigePolygon,  471, Anna Salai,Teynampet,Chennai-600018  T+914442940000 | **DEHRADUN**  SuiteNo2211,2ndFloor,Building 2000, MichiganAvenue, Doon ExpressBusiness Park,  Subhash Nagar,Dehradun-248002  T+911352646500 | **GURGAON**  21stFloor,DLFSquare,Jacaranda Marg, DLFPhaseII,  Gurgaon- 122002  T+911244628000 | **HYDERABAD**  7th Floor,BlockIII,WhiteHouse,  Kundan Bagh,Begumpet,Hyderabad-500016  T+914066308200 | **KOCH**I  6thFloor,ModayilCentrePoint, Warriam RoadJunction, MGRoadKochi-682016  T+914844064541 |
| **KOLKATA**  10CHungerfordStreet,5th Floor,  Kolkata-700017  T+913340508000 | **MUMBAI**  11thFloor,TowerII,  One International Center,SB Marg Prabhadevi (W),Mumbai-400013  T+912266262600 | **MUMBAI**  Kaledonia,1stFloor,C Wing, (OppositeJ&J Office),  Sahar Road,AndheriEast,  Mumbai-400 069 | **NOIDA**  PlotNo19A,2ndFloor,Sector-16A,  Noida-201301  T+911204855900 | **PUNE**  3rdFloor,UnitNo309-312, West Wing, NyatiUnitree, Nagar Road,Yerwada  Pune-411006  T+912067448800 |

Formoreinformationorforanyqueries,writetousat[**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Followus@GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts asthe Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and MediumEnterprise(MSME)sectoraswellasforco-ordinationoffunctionsofinstitutionsengagedinsimilaractivities.Inthecontext of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBIVision2.0whichenvisagesanintegratedcreditanddevelopmentsupportroleoftheBankbybeingathoughtleader,adoptingacredit-plusapproach,creating amultipliereffectand servingasanaggregatorinMSMEspace.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementingagency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any actiontakenbyitbasedonthisdocument.SIDBI,itsdirectors,employeesoranyofficeshallnotbeliableforlossofwhatsoevernaturearising byusingthecontentofthisdocument.*