

FortnightlyReport

SIDBI – PMU Madhya Pradesh

**Period–15th– 31stJanuary 2023**

**Project Progress Report–Fortnightly**

|  |  |
| --- | --- |
| **SIDBIUP statePMUfor MSME** | |
| **Location: Bhopal**  **Month & Year: December2022**  **Fortnight Ending: December 31,2022** | **ReportSummary**  This report includes the activities carried out bySIDBI-PMU fort he  Facilitation of MSM Ecosystem in the State of Madhya Pradesh. |

**TeamDeploymentStatus**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Nameof Resource** | **DeploymentDate** |
| 1 | PMUManager | Binu Chaturvedi | 9th Jan 2023 |
| 2 | BusinessAnalyst | Mohammed Zafar | 9th Jan 2023 |

**Details of State Nodal Connect - Name – Shri Pankaj Dubey, Dy.Director,Department of MSME, Mobile: 9179831101, Email:** [pankaj.dubey25@mp.gov.in](mailto:pankaj.dubey25@mp.gov.in)

**Activities performed by PMU during fortnight ending January 31, 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| 1. **Onboarding of SIDBI PMU GT Madhya Pradesh**  * SIDBI PMU MP started its operation from 9th Jan 2023. Shri. P. Narahari, Commissioner Industries cum Secretary, Govt of MP, Department of MSME is the HOD of the dept and PMU reports to him, whereas. Shri. Pankaj Dubey, Dy. Director, MSME Directorate has been assigned as a nodal officer of the SIDBI-PMU. | |
| 1. **Inception meeting between Department of MSME & SIDBI PMU (GT) (Annexure 1)**  * Inception meeting to initiate MSME-SIDBI project was held on **17th January 2023 that** was. Chaired by Shri. P Narahari, Commissioner Industries cum Secretary, GoMP, MSME Department. AGM SIDBI, Bhopal and officers from the MSME Department participated along with the team leader of Grant Thornton SIDBI PMU (implementing agency), PMU team, and MPLUN officers. | |
| 1. **Meeting with Director MSME to appraise about PMU scope of work (Annexure 2)**  * PMU Team had a fruit full discussion with Shri. Rohit Singh, IAS, Director Industries, MD MPLUN, GoMP, where PMU team explained about their scope of work and incorporated department expectation from SIDBI PMU. The meeting was held on 23rd Jan 2023 | |
| 1. **MP PMU Draft Action Plan (Jan-Sept 2023) (Annexure 3)**  * As directed in the Inception meeting, in compliance to the directions PMU Team in consultation with Department of MSME and SIDBI drafted a work plan of the proposed activities and submitted to SIDBI same would be shared to the Department of MSME in due course. | |
| 1. **Draft concept note for MPLUN Strengthening as MSME PSU**  * PMU Team started working on it, collecting data, details from stakeholders and other similar nature of PSUs and working on concept note for strengthening of MPLUN. This is one of the major deliverable expected by the department of MSME from PMU. * To perform this activity, multiple consultation meetings were done with MPLUN, MPIDC and Department of MSME senior officers and stakeholders to assess the strength, weakness of MPLUN and expectations of the department. | |
| 1. **SCDF**  * PMU Team had a fruitful discussion with Finance Adviser and Additional Secretary cum Director Institution Finance of the Finance Ministry of the Government of MP and discusses the scope of SCDF. * PMU Team has requested to the Additional Chief Secretary, GoMP Finance Dept for an appointment with him to schedule a meeting with SIDBI concern officers for the discussion on SCDF and other activities of SIDBI. | |

|  |
| --- |
| **ActionableandSupportrequired** |
| * To provide guidance and support in the implementation of various activities of the project |
| **ActivitiesWayforward** |
| * To Explore potential departments of GoMP having requirement of SCDF * To conduct one day orientation program for District level MSME officers (GM DTICs) * To draft a concept note for the strengthening of MPLUN |
| **InputsofState NodalConnect/Officer** |
| 1. Strengthening of MPLUN |

**Contactus**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices asmentionedbelow:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEWDELHI**  National Office,Outer Circle, L 41,Connaught Circus,New Delhi - 110001T+911142787070 | **NEWDELHI**  6thFloor,Worldmark2,Aerocity,  New Delhi - 110037T+911149527400 | **AHMEDABAD**  7thFloor,HeritageChambers,  Nr Azad Society,Nehru Nagar,Ahmedabad-380015 | **BENGALURU**  5thFloor,65/2,BlockA,Bagmane Tridib,Bagmane Tech Park,CV Raman Nagar,Bengaluru-560093  T+918042430700 | **CHANDIGARH**  B-406A, 4th Floor, L&TElante Office Building,IndustrialAreaPhaseI,Chandigarh -160002  T+911724338000 |
| **CHENNAI**  7thFloor,PrestigePolygon,  471, Anna Salai,Teynampet,Chennai-600018  T+914442940000 | **DEHRADUN**  SuiteNo2211,2ndFloor,Building 2000, MichiganAvenue, Doon ExpressBusiness Park,  Subhash Nagar,Dehradun-248002  T+911352646500 | **GURGAON**  21stFloor,DLFSquare,Jacaranda Marg, DLFPhaseII,  Gurgaon- 122002  T+911244628000 | **HYDERABAD**  7th Floor,BlockIII,WhiteHouse,  Kundan Bagh,Begumpet,Hyderabad-500016  T+914066308200 | **KOCH**I  6thFloor,ModayilCentrePoint, Warriam RoadJunction, MGRoadKochi-682016  T+914844064541 |
| **KOLKATA**  10CHungerfordStreet,5th Floor,  Kolkata-700017  T+913340508000 | **MUMBAI**  11thFloor,TowerII,  One International Center,SB Marg Prabhadevi (W),Mumbai-400013  T+912266262600 | **MUMBAI**  Kaledonia,1stFloor,C Wing, (OppositeJ&J Office),  Sahar Road,AndheriEast,  Mumbai-400 069 | **NOIDA**  PlotNo19A,2ndFloor,Sector-16A,  Noida-201301  T+911204855900 | **PUNE**  3rdFloor,UnitNo309-312, West Wing, NyatiUnitree, Nagar Road,Yerwada  Pune-411006  T+912067448800 |

Formoreinformationorforanyqueries,writetousat[**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Followus@GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts asthe Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and MediumEnterprise(MSME)sectoraswellasforco-ordinationoffunctionsofinstitutionsengagedinsimilaractivities.Inthecontext of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBIVision2.0whichenvisagesanintegratedcreditanddevelopmentsupportroleoftheBankbybeingathoughtleader,adoptingacredit-plusapproach,creating amultipliereffectand servingasanaggregatorinMSMEspace.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementingagency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any actiontakenbyitbasedonthisdocument.SIDBI,itsdirectors,employeesoranyofficeshallnotbeliableforlossofwhatsoevernaturearising byusingthecontentofthisdocument.*