

Fortnightly Report

SIDBI – PMU Uttar Pradesh

**Period – 15th – 31st December 2022**

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI UP state PMU for MSME** | |
| **Location: Lucknow**  **Month & Year: December 2022**  **Fortnight Ending: December 31, 2022** | **Report Summary**  This report includes the activities carried out by SIDBI - PMU for the  facilitation of MSME ecosystem in the State of Uttar Pradesh. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | PMU Manager | Jitendra Kumar | 6th Oct 2020 |
| 2 | Business Analyst | Mohammed Zafar | 6th Oct 2020 |

**Details of State Nodal Connect - Name – Ms. Ayushi Baranwal, Assistant Commissioner UP MSME, Mobile: 7800836855. Email:** [**odopcell@gmail.com**](mailto:odopcell@gmail.com)

**Activities performed by PMU during fortnight ending December 31, 2022**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| 1. **MoU between SIDBI and AICMA, Bhadohi, U.P (Annexure 1&2)**  * PMU in consultation with SIDBI ROLK and AICMA prepared a draft MoU between AICMA and SIDBI. MoU is shared with AICMA for their reference and necessary action. AICMA had called EC meeting to take decision on MoU with SIDBI This MoU will facilitate MSMEs in the aforesaid cluster and hence, meet ballooning requirement of WC/TL from SIDBI. This MoU is likely to be signed in the month of January 2022. | |
| 1. **Udhyam Sangyan Programme**  * PMU in consultation with ROLK is planning to organize Udhyam Sangyan Programme with Reliance Industries, Barabanki Plant. Around 30 MSME units specially in manufacturing of Fiber (cable). PMU also, coordinating with IAs for mobilizing these MSME units. This activity will probably will took place in January 2023. | |
| 1. **General agreement with RRBs**  * In accordance to RBI circular SIDBI ROLK through PMU is facilitating General Agreement with RRBs in UP. In this regard, PMU had approached 3 RRBs in the state- 1. Prathama Bank 2. Baroda bank of UP and 3. Aryavart Bank.   **Status Update on General Agreement with 3 RRB in UP are-**   1. **Prathama Bank**- GE to be done in January 2023 in Moradabad 2. **Baroda bank**-As discussed with the bank Mr. Sanjiv that bank is not in a favour of General Agreement. However, he suggested to had a discussion with their sponsor bank GM in Lucknow. 3. **Arayavat Bank-**On 15-12-2022, physical meeting was conducted with Arayavat Bank with DGM Shreekanta Das and PMU Team. RRB said to put up the GE in their board meeting in first week of January 2023. However, a meeting is proposed with chairman Aryavat Bank and ROLK GM before MoU signing off ceremony | |
| 1. **Arrangement on Parbat Mahotsav (Annexure 3)**  * PMU Team is preparing blue print w.r.t. Parbat Mela schedule from 14th January to 23rd 2023 to be held in Lucknow, UP. * Around 30 Stalls in the aforesaid mela are sponsored by SIDBI ROLK | |
| 1. **Pledge scheme assumptions (Annexure 4)**  * PMU Team prepared postulation document with the inputs from UPSIC officials and taking average of established parameters. * Here PMU have implicit two scenario - (A) 1 Park/2 Districts and (B) 2 Parks/3 Districts. The attached excel provides working of the outcome. | |
| 1. **SCDF update –**   PMU Team had facilitated SCDF in the State, details of which are-   * Rs 1000 Cr. in principle approval has been given to MSME dept. UP * On 29th Aug 2022- SIDBI had given In-principle approval of INR 2,000 crore to Energy Department * GM, SIDBI along with PMU team met new ACS MSME and briefed about the SCDF progress. ACS indicated that he would take up the case with finance department and inform accordingly. Initiatives to reach out to other departments * **PWD Department (Road etc.)** - A meeting was held with the Special Secretary, PWD, GoUP on August 22, 2022, to request speeding up submission of fund requirement demand (INR 1223 Cr) generated by the UP-State Bridge Corporation to finance department. The demand letter reached out to ACS, Finance (September 15, 2022) for further forwarding to SIDBI for in principle approval. Further a meeting was held with ACS finance to expedite the process of forwarding the demand (of PWD) to SIDBI * **Energy Department** - Follow up with energy department officials to request speeding up submission of fund requirement demand (INR 8113 Cr) generated by UPPCL. (August 21-22, 2022). Post in principle approval of INR 2000 cr, on September 15, 2022, DGM SIDBI along with PMU team met with senior officials of UPCL and briefed about the provisioning of the SCDF fund and expected requirements in selection of projects under the SCDF. On November 15, 2022 PMU team meet Director of Finance, UPCL and reiterated the request for selection of the projects. On December 7 and December 12, 2022 PMU team again met the officials to convey that provided list of projects cannot covered under SCDF and another project should be identified and shared at the earliest. * **MSME Department** – September 29, 2022, PMU team along with GM, SIDBI met ACS, MSME dept and requested to take forwarding letter from the finance department for one project already submitted to SIDBI. On October 31 2022, the PMU team meet with Mr. Pranjal Yadav, Secretary MSME to communicate the departmental action plan to utilize SCDF. On November 02, 2022, GM SIDBI and PMU team meet Director of Industries, MSME and requested him to take forwarding letter from the finance department for one project already submitted to SIDBI. On December 6, 2022 PMU team along with the GM. SIDBI meet ACS, MSME and discussed PLEDGE schemes for Private Industrial Parks in which, it is proposed to create a corpus of INR 500cr with the help of SCDF. * **Meeting with Finance Department** - September 21, October 5, October 31, November 14, December 1, December 13, 2022 PMU team reached out to Finance Department and requested to forward the request of PWD demand letter to SIDBI for in-principle approval. PMU team also briefed out about the requirement of master agreement between government and SIDBI and initiating process to get RBI Mandate. | |

|  |
| --- |
| **Actionable and Support required** |
| * State Government to roll out State CGTMSE scheme after MoU * State Government to on-board TReDS platform- RXIL |
| **Activities Way forward** |
| * Vendor development programme with Tata Motors * Visit to Bhadohi for Model Cluster Financing Instrument and meeting with AICMA * General Agreement with SIDBI and RRBs in UP * MoU with AICMA and SIDBI |
| **Inputs of State Nodal Connect / Officer** |
| 1. SIDBI to collaborate with State Government for GIS 2023 |

**Snapshot of the activities-**

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*