

FortnightlyReport

SIDBI – PMU Madhya Pradesh

**Period–15th to 31st March 2023**

**Project Progress Report–Fortnightly**

|  |  |
| --- | --- |
| **SIDBI MP State PMU for MSME** | |
| **Location: Bhopal (MP)**  **Month & Year: March 2023**  **Fortnight Ending: 31th March 2023** | **ReportSummary**  This report includes the activities carried out by SIDBI-PMU for the  Facilitation of MSM Ecosystem in the State of Madhya Pradesh. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Nameof Resource** | **DeploymentDate** |
| 1 | PMU Manager | Binu Chaturvedi | 9th Jan 2023 |
| 2 | Business Analyst | Mohammed Zafar | 9th Jan 2023 |

**Details of State Nodal Connect - Name – Shri Pankaj Dubey, Dy.Director,Department of MSME, Mobile: 9179831101, Email:** [pankaj.dubey25@mp.gov.in](mailto:pankaj.dubey25@mp.gov.in)

**Activities performed by PMU during fortnight ending March 31, 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| 1. **State CGTMSE Scheme**  * A very fruitful meeting on CGTMSE was held today jointly chaired by Commissioner Industries GoMP and Mr. Sandeep Verma CEO CGTMSE . Representatives of SLBC banks, including senior officers from SBI, CBI, PNB, BOI, UCO, MSME and the SIDBI PMU team attended. * An overview of CGTMSE salient features and anticipated changes was presented by the CEO. * For allocating corpus funds to address the gaps, the GoMP principally agreed to execute the MOU with CGTMSE subject to the Finance department's consent. * Later on SIDBI PMU team had an exclusive meeting with the CEO CGTMSE | |
| 1. **PMU Action Plan**  * PMU team had a detailed presentation of Annual Action Plan before MSME officers from directorate, chaired by director Industries. It was suggested to include training need assessment various vertical department of MSME Directorate. | |
| 1. **RAMP SIP**  * PMU was directed to support in implementation of RAMP activities- as and when basis | |
| 1. **Concept Note on one day training program of GM DTICs**  * PMU team prepared concept note and detailed agenda for organizing one day training cum orientation program of GM DTICs and supporting staff on cluster development, preparation of DSR and DPR etc. | |
| 1. **PMU Tracker**  * Under maintenance and updating of PMU tracker following issues were resolved by PMU- * SIDBI officials (verifier/approver) not mapped (Rajasthan) * SIDBI verifier/approver not able to do their task (UP, Delhi etc) * Old test file uploaded still exists. * Creation of Login ID for all SIDBI State/RO office. | |

|  |
| --- |
| **Actionable and Support required** |
| * To provide guidance and support in the implementation of various activities as per action plan |
| **ActivitiesWayforward** |
| * To Explore potential departments of Go MP having requirement of SCDF * Strengthening of DTICs * Strengthening of MPLUN as an exclusive corporation of MSME department * To conduct one day orientation program for District level MSME officers (GM DTICs) * CGTMS orientation |
| **Inputs of State Nodal Connect/Officer** |
| 1. Strengthening of MPLUN 2. On various planed activities for implementation |

**Snapshot of performed activities-**

|  |  |
| --- | --- |
| Figure PMU Manager Shri. Binu Chaturvedi giving presentation on MPLUN | Figure 2 PMU Manager Shri. Binu Chaturvedi giving presentation on MPLUN |

**Contactus**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices asmentionedbelow:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEWDELHI**  National Office,Outer Circle, L 41,Connaught Circus,New Delhi - 110001T+911142787070 | **NEWDELHI**  6thFloor,Worldmark2,Aerocity,  New Delhi - 110037T+911149527400 | **AHMEDABAD**  7thFloor,HeritageChambers,  Nr Azad Society,Nehru Nagar,Ahmedabad-380015 | **BENGALURU**  5thFloor,65/2,BlockA,Bagmane Tridib,Bagmane Tech Park,CV Raman Nagar,Bengaluru-560093  T+918042430700 | **CHANDIGARH**  B-406A, 4th Floor, L&TElante Office Building,IndustrialAreaPhaseI,Chandigarh -160002  T+911724338000 |
| **CHENNAI**  7thFloor,PrestigePolygon,  471, Anna Salai,Teynampet,Chennai-600018  T+914442940000 | **DEHRADUN**  SuiteNo2211,2ndFloor,Building 2000, MichiganAvenue, Doon ExpressBusiness Park,  Subhash Nagar,Dehradun-248002  T+911352646500 | **GURGAON**  21stFloor,DLFSquare,Jacaranda Marg, DLFPhaseII,  Gurgaon- 122002  T+911244628000 | **HYDERABAD**  7th Floor,BlockIII,WhiteHouse,  Kundan Bagh,Begumpet,Hyderabad-500016  T+914066308200 | **KOCH**I  6thFloor,ModayilCentrePoint, Warriam RoadJunction, MGRoadKochi-682016  T+914844064541 |
| **KOLKATA**  10CHungerfordStreet,5th Floor,  Kolkata-700017  T+913340508000 | **MUMBAI**  11thFloor,TowerII,  One International Center,SB Marg Prabhadevi (W),Mumbai-400013  T+912266262600 | **MUMBAI**  Kaledonia,1stFloor,C Wing, (OppositeJ&J Office),  Sahar Road,AndheriEast,  Mumbai-400 069 | **NOIDA**  PlotNo19A,2ndFloor,Sector-16A,  Noida-201301  T+911204855900 | **PUNE**  3rdFloor,UnitNo309-312, West Wing, NyatiUnitree, Nagar Road,Yerwada  Pune-411006  T+912067448800 |

Formoreinformationorforanyqueries,writetousat[**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Followus@GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts asthe Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and MediumEnterprise(MSME)sectoraswellasforco-ordinationoffunctionsofinstitutionsengagedinsimilaractivities.Inthecontext of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBIVision2.0whichenvisagesanintegratedcreditanddevelopmentsupportroleoftheBankbybeingathoughtleader,adoptingacredit-plusapproach,creating amultipliereffectand servingasanaggregatorinMSMEspace.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementingagency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any actiontakenbyitbasedonthisdocument.SIDBI,itsdirectors,employeesoranyofficeshallnotbeliableforlossofwhatsoevernaturearising byusingthecontentofthisdocument.*