

Fortnightly Report

SIDBI – PMU Rajasthan

Period – 15th March to 31st March 2023

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Rajasthan**  **Month & Year: March 2023**  **Fortnight Ending: 31st March 2023** | **Report Summary**  This report includes the activities carried out by SIDBI - PMU for the  facilitation of MSME Ecosystem in the State of Rajasthan. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | PMU Manager | Ashish Kumar | 03rd January 2022 |
| 2 | Business Analyst | Ashutosh Kumar | 14th September 2020 |

**Details of State Nodal Connect - Name – Mr. S.S. Shah Contact – 0141-2227727 (Additional Director)**

**Activities performed by PMU during fortnight ending 31st March 2023.**

|  |  |
| --- | --- |
| **Sl. No.** | **Details of Activities Carried Out** |
| **General Activities to Facilitate Project Implementation** | |
| 1. **“Ease of Doing Business (EoDB)”: -** PMU team prepared a detailed presentation for Chief Secretary, GoR pertaining to suggestions on improvement in current scenario / status of **“Doing Business in Rajasthan”**. (Annx-1) | |
| 1. **SCDF: -** PMU team coordinated with Chief Secretary office and Finance Department, GoR in order to finalize nominations for one day workshop on **“Making Future Ready Sustainable Cluster Infrastructure”** to be held on 15th April 2023 at Goa. (Annx-2) | |
| 1. **SCDF: -** Facilitating a **third-party report on MSME linkage** for the approved project of PHED Department. PMU team coordinating with PHED department and discussion going on with impaneled agencies to get quotation from them and further issuance of work order of the same as soon as possible. | |
| 1. **Mukhyamantri MSME Suraksha Yojana: -** PMU team discussed with Commissioner Industries regarding comparative proposal form United India Insurance Company Limited and New India Assurance Limited. Currently department is evaluating this and we are waiting further requirement from the department on this scheme. | |
| 1. **Social Security Scheme for Artisan and Weavers: -** PMU team discussed with the Commissioner Industries regarding further requirement from the department on this scheme. We are also coordinating with LIC regional team to submit the asked proposal as soon as possible. | |
| 1. **REPC: -** PMU team successfully coordinated the **“Rajasthan International Export Expo 2023”** event organized on 20th to 22nd March 2023. Supported Industries Department and REPC (Rajasthan Export Promotion Council) in organizing the event and helped them connecting with various Industrial Associations, delegates and invitees. | |
| 1. Interacted with visiting entrepreneurs (in MIFC) and made them aware regarding different suitable schemes of State Government & GoI. | |

|  |
| --- |
| **Actionable and Support required** |
| 1. SCDF, 2. Treds, 3. RAMP |
| **Activities Way forward** |
| 1. Mukhyamantri MSME Suraksha Yojana, 2. Social Security Scheme for Artisan and Weavers |
| **Inputs of State Nodal Connect / Officer** |
| Good work by SIDBI PMU Team |

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

**Contact us**

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*