­­-



Fortnightly Progress Report

SIDBI – PMU Assam

Period –15th to 31st March 2023

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Assam**  **Month & Year: February 2023**  **Fortnight Ending: 28th February 2023** | **Report Summary**  This Report includes the activities carried out by SIDBI - PMU for the  facilitation of MSME Ecosystem in the State of Assam. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | PMU Manager | Revant Bhattacharjee | 11 October 2022 |

**Details of State Nodal Connect –**

**Activities performed by PMU during fortnight ending 31st March 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| **General Activities to facilitate project implementation** | |
| 1. Meetings with GM, Assam Industrial Development Corporation (AIDC) for the purpose of addressing concerns regarding CGTMSE & ASVCF as raised by the Industries Department GoA. The prime focus being on the implications arising from their operationalization. | |
| 1. Meeting with GM (Tech), for proposing MSME Infrastructure possibilities (facilitation of conveyance to proposed industrial estates) with the help of a dedicated ropeway from main land to industrial area cutting down on transport time. | |
| 1. Facilitated the nomination of two senior officials from Finance Department, GoA for attending the SCDF conclave scheduled to take place on 15th April, 2023 in Goa. | |
| 1. Prepared 2-page concise document for circulation to concerned GoA departments from SIDBI BO end, for the purpose of sensitizing about the various technicalities of CGTMSE & ASVCF schemes. | |
| 1. Facilitated and received the first consent from Ministry of Finance, GoI to Finance Department, GoA amounting to Rs. 60 crore for FY 2022-23 under Article 293(1)/ (3) | |

|  |
| --- |
| **Actionable and Support required** |
| 1. BO, EZO, HO support required for persuading concerned GoA departments for availing maximum possible borrowing consent under Arcticle 293(3)/ (1) for FY 2023-24 |
| **Activities Way forward** |
| 1. Pursue CGTMSE and ASVCF operationalization 2. Following up SCDF borrowing with Finance, EA and IC&PE Department, GoA |
| **Inputs of State Nodal Connect / Officer** |
|  |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*