

Fortnightly Report

SIDBI – PMU J&K

Period – 31-Jan-2023

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: J&K**  **Month & Year: Jan- 2023**  **Fortnight Ending: 31st Jan 2023** | **Report Summary**  This Report includes the activities carried out by SIDBI - PMU for the  Facilitation of MSME Ecosystem in the UT J&K |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | PMU Manager | Narinder Abrol | 01 Nov 2022 |
| 2 | Business Analyst | Mohammad Rafiq | 6th June 2022 |

**Details of State & SIDBI Nodal Connect –**

**Name: Ms Smita Sethi (MD SIDCO/SICOP) Nodal Officer for J&K.**

**Name – Shri Balbir Singh, General Manager Mobile 8511104774, Email: balbir@sidbi.in- Shri Sanwal Dogra MGR, Mobile: 6390222280, Email:** [**sanwal@sidbi.in**](mailto:sanwal@sidbi.in)

**Activities performed by PMU during fortnight ending 31st Jan-2023**

|  |  |  |
| --- | --- | --- |
| **Activity** | **Details of activities carried out** | |
| **General Activities to facilitate project implementation** | | |
| **16-Jan-23** | **Secretary Industries and Commerce** | Met with Secretary I&C and enquired about SCDF and PMU extension letters. Then met with Assistant Director codes and Director General Codes and checked with them the letters already submitted for SCDF. Then met with Director Planning Tourism and enquired about the first meeting of committee formed especially for SCDF projects. |
|  | **Assistant Director Codes** |
|  | **Director General Codes** |
|  | **Director Tourism** |
| **17-Jan-23** | **Director General Codes** | Met with Director General Codes and checked with him about the SCDF letter and submitted Principle Commitment Letter to him. After this asked him to forward the same letter to concerned Next officer. Then met with Director Finance resources and checked with him if he has received the letter from DG codes. He checked the letter and asked his team to work on it. |
|  | **Director Finance Resources** |
|  | **Secretary Industries and Commerce** | Met with Secretary Industries and commerce and enquired about SCDF and PMU extension letter. Discussed various issues regarding the SCDF status, also confirmation for VC with Principal Secretary Sir. |
| **18-Jan-23** | **Director Resources & Director General Codes** | Met with the Director Resources for SCDF file status |
| **19-Jan-23** | **Secretary I&C** | Met with Secretary I&C for SCDF and PMU extension letter. Then met with Director Finance Industries for the same. Later on met with Technical officer Smart City Jammu and checked the scope for SCDF with him. |
|  | **Technical officer Smart City Jammu** |
| **20-Jan-23** | **MD SIDCO & SICOP** | Met with MD SIDCO SICOP and collected list of industrial estates area wise and one DPR. Then prepared data for the meeting to be held on 23- Jan with PS I&C. Then apprised him about the progress of PMU work in J&K. |
| **23-Jan-23** | **PA to PS I&C** | Met with PA to PS I&C and checked his availability for 25-Jan. Then met with DG Codes and checked SCDF letter status with him. |
| **24-Jan-23** | **PA to PS I&C** | PMU met with PA to PS I&C and checked with him about the virtual schedule of meeting for 25th Jan. |
|  | **Director Finance resources** | Later on, PMU met with Director Finance Resources and checked the status of SCDF letter pending at his desk. |
|  | **E-MDP Programme** | PMU also facilitated SKUAST Kashmir Innovation Incubation & Entrepreneurship (SKIIE) centre, one week E-MDP Programmes to MSEs with SIDBI’s Schemes and its Initiative in J&K |

|  |  |  |
| --- | --- | --- |
| **25-Jan-23** | **Principle Secretary** | PMU also facilitated virtual Meeting of Principle Secretary with SIDBI Central Team |
|  | **GM SIDCO** | PMU Collated and prepared Industrial estate data of J&K for the meeting scheduled with PS I&C, Met with GM SIDCO and got updated IE data from him. |
| **27-Jan-23** | **Deputy Director Planing (Tourism)** | Follow-up with the Officer in concern to arrange first ever general meeting of the Committee comprise especially for SCDF projects |
| **27-Jan-23** | **PHDCCI** | PMU had a meeting with PHDCCI for Exposure visit to Wool cluster and various capacity building programmes for Artisans scheduled in Feb-23 |
| **30-Jan-23** | **Concept Note of Wool Cluster** | PMU prepared the concept note of wool cluster to PHDCCI in J&K |
|  | **Secretary I&C** | Met with Secretary I&C and discussed about her input for the presentation to be given to Principle Secretary I&C. |
| **31-Jan-23** | **PA to Secretary I&C** | Then met with PA to Secretary I&C and Director Finance resources and checked the status of SCDF MoU file. |
|  | **Director Finance resources** |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*