

Fortnightly Report

SIDBI – PMU J&K

Period – 01-Jan-23 to 15-Jan-2023

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: J&K**  **Month & Year: Jan- 2023**  **Fortnight Ending: 15th Jan 2022** | **Report Summary**  This Report includes the activities carried out by SIDBI - PMU for the  Facilitation of MSME Ecosystem in the UT J&K |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | PMU Manager | Mohammad Rafiq | 6th June 2022 |
| 2 | Business Analyst | Narinder Abrol | 01 Nov 2022 |

**Details of State & SIDBI Nodal Connect –**

**Name: Ms Smita Sethi (MD SIDCO/SICOP) Nodal Officer for J&K.**

**Name – Shri Balbir Singh, General Manager Mobile 8511104774, Email: balbir@sidbi.in- Shri Sanwal Dogra MGR, Mobile: 6390222280, Email:** [**sanwal@sidbi.in**](mailto:sanwal@sidbi.in)

**Activities performed by PMU during fortnight ending 31st Dec-2022**

|  |  |  |
| --- | --- | --- |
| **Activity** | **Details of activities carried out** | |
| **General Activities to facilitate project implementation** | | |
| **02-Jan-23** | **Secretary Industries and Commerce** | Met with Secretary Industries and commerce and enquired about SCDF and PMU extension. Discussed various issues regarding the SCDF status. |
| **03-Jan-23** | **Letter of Intent between SIDBI and DOI&CJK** | Prepared Letter of Intent template for coming into agreement with Directorate of Industries and Commerce JK and shared the same for final vetting to Chandigarh office. |
| **05-Jan-23** | **Letter of Intent between SIDBI and IEIGC Lassipora, Pulwama, JK** | Prepared Letter of Intent template for coming into agreement with and IE-IGC Lassipora, Pulwama Jammu Kashmir and shared the same for final vetting to Chandigarh office. |
| **Director Tourism** | Met with the Officer in concern to arrange first ever general meeting of the Committee comprise especially for SCDF projects. |
| **06-Jan-23** | **Secretary I&C** | Met with Secretary Industries and commerce and enquired about SCDF and PMU extension. Discussed various issues regarding the SCDF status. Then met with Director Finance resources, Director General Codes, Deputy Director Codes and Checked for final legal and financial vetting of submitted documents by SIDBI to the department for SCDF. |
| **Director Finance Resources** |
| **Director general Codes** |
| **09-Jan-23** | **Deputy Director Codes** |
| **Director Finance Planning** |
| **11-Jan-23** | **MD SICOP & SIDCO** | Met with MD of SICOP and SIDCO and make him aware about SIDBI and its schemes. Then met with Director I&C and made her aware of Green financing schemes of SIDBI and asked for notifications during the awareness campaigns of DIC J&K in the whole UT of Jammu Kashmir. Director I&C has been requested to instruct all DICs to include SIDBI into all the DIC awareness campaigns in the UT of Jammu and Kashmir. |
| **Director I&C** |
| **12-Jan-23** | **Secretary I&C** | Went to SIDBI office, then met with Secretary I&C, Director Finance Industries, Director General Codes, Deputy Director Codes and personal Section of Chief Secretary and enquired about the status of SCDF letter. As required by the Director General Codes, the Principle Commitment Letter is required to be submitted and the same was submitted to the Director general codes as requested by them. |
| **Director Finance Industries** |
| **Director general Codes** |
| **Chief Secretary office** |
| **13-Jan-23** | **IE Samba** | Went to Industrial estate Samba along with Branch Head Sidbi jammu and met with one of the promoters there. Later went to Industrial estate Bari Brahmana and met with the second MSE units there. |
| **IE Bari Brahmana** |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*