

Two Month Progress Report

SIDBI – PMU Assam

Period – January & February 2023

**Project Progress Report – January & February 2023**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location:** Guwahati  **Month & Year:** January & February 2023  **Ending:** 28th February 2023 | **Report Summary**  This Report includes the activities carried out by SIDBI - PMU for the facilitation of MSME Ecosystem in the State of Assam. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **S. No** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | PMU Manager | Revant Bhattacharhee | October-2022 |

**Details of State Nodal Connect –**

**From SIDBI –** Shri Sibi R. SIDBI AGM (BO-Guwahati)

**From Directorate of Industries, GoA:**

**Activities performed by PMU**

|  |
| --- |
| **Details of activities carried out** |
| **Improved Governance Framework/ Policy Advocacy** |
| 1. Policy advocacy for Green Finance scheme, raising approximately 1.2 Cr of proposals |
| 1. Engaged in advocacy drives for STHAPAN and ARISE schemes on behalf of SIDBI and identified prospective leads. |
| **Enhancing Credit Flow to MSMEs** |
| 1. Constant follow ups being done with the Economic Affairs Dept., Govt. of Assam for pursuing the approval and subsequent operationalisation of the CGTMSE and ASVCF schemes. PMU has been responding to numerous queries being raised by the EA Department regarding the various technicalities of the CGTMSE & ASVCF schemes. |
| 1. PMU has been following up with FINER, for identifying the status of executing MoU with RXIL, to expedite their on boarding to TReDS platform. Working around issues stated by FINER. |
| 1. Collaboration of SIDBI with NedFi to facilitate ‘**Prarambh**’. A conclave for new startups and interested investors, educating and funding them to raise their first cheque. Mobilised approximately 50 Lac worth of funding for new start-ups |
| 1. Arranged and facilitated CGM EZO visit to facilitate identification and prompt resolution of bottlenecks from GoA end in the operationalisation of CGTMSE & ASVCF. |
| **Strengthening Infrastructure for MSMEs** |
| 1. Planning, facilitating and engaging in **UDYAM 2023**, a two-day vendor awareness program organized by MSME DFP Guwahati, with SIDBI being a key stakeholder. Aided technical sessions and aided numerous MSME to overcome bottlenecks in bidding for PSU tenders and also maintaining adequate liquidity. |
| 1. Convergence with MSME DI for imparting financial literacy and MDPs. Proposals being prepared to be submitted for approval for appraisal and approval in next FY. |
| **SCDF** |
| 1. Aided CGM EZO SIDBI meeting with the new Commisioner & Secretary, Dept. of Finance and Secretary, Industries, Commerce & P.E Dept. to identify and resolve issues hindering the GoA availing loans under SCDF |
| 1. Facilitated letter expressing willingness of SIDBI to grant 1000Cr worth of loans to GoA and invited additional proposals for the same along with accommodation of projected sanction amount in Article 293(3) for the upcoming FY. |
| **Cluster Financing** |
| 1. NEHHDC under Ministry of DoNER proposed the upskilling 500+ non-farm artisans in 6 clusters from 3 different states is being pursued. Completed re drafting of proposal, awaiting DGM approval. |
| 1. Identifying clusters eligible for soft intervention through SIDBI Care – to save a dying art. Routine meeting with DGM SIDBI for appraisals and selection of provided options. |
| **Others** |
| 1. Drafted proposal with P&D team for TRTC & IIE initiated vocational training program for eligible youth – 2 batches of 30 individuals each. Proposal has been sent to SIDBI EZO for approval – 1) Data Entry 2) Factory Floor Man training |
| 1. Completed re-drafting revised proposal for Swavalamban Hunarbaaz – identifying bottlenecks and charting a revised course of action for the effective operationalising of the scheme with the IAs. Also engaged in meetings with IAs for receiving additional delivaerables. |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*