

Monthly Progress Report

SIDBI – PMU Chhattisgarh

Period – January 2023

**Project Progress Report – Monthly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Chhattisgarh**  **Month & Year: January, 2023**  **Month Ending: January, 2023** | **Report Summary**  This Report includes the activities carried out by SIDBI - PMU for the  facilitation of MSME Ecosystem in the State of Chhattisgarh. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | PMU Manager | Ishwar Kumar | 08th August 2022 |
| 2 | Business Analyst | Shubham Jha | 07th November 2022 |

**Details of State Nodal Connect - Name – Shri Anil Tuteja (IAS), Director Industries, Chhattisgarh.**

**Shri Sanjay Gajghate, Joint Director Industries, Chhattisgarh.**

**Activities performed by PMU in the month of January and February 2023**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **S. No** | **Theme** | **Intervention** | **Work completed** | **Work completed by PMU but pending with the state Govt./others** | **Work in Progress** | **Work not yet started** |
| **1** | **Policy Advocacy/**  **Governance** | Preparation of Export Procedure Handbook |  |  | The Handbook is being prepared |  |
| Conduct diagnostic study to understand the export potential of the state and prepare an export strategy document |  |  |  |  |
| Prepare a Compendium of schemes for MSMEs | Draft copy prepared | Forwarding letter from state govt. is pending |  |  |
| Develop a State MSME Profile | Draft copy prepared | Forwarding letter from state govt. is pending |  |  |
| Unplanned Activity | * Prepared State Logistics Policy * Provided support to state government in preparing a women entrepreneurship policy |  |  |  |
| **2** | **Enhancing credit flow to the MSME sector** | TReDS Implementation for MSMEs-Registration of MSMEs and CG Govt. supported institutions as sellers and buyers on TReDS Platforms |  | PMU organized meetings with facilitating platforms and submitted a request to the DIF for onboarding of 2 Departments or State corporation on TReDs Platform | The Proposal submitted by PMU is still consideration by the Finance Department |  |
| Promote Green Energy Financing by developing linkages between Financial Institutions and Industry Associations, CREDA, Energy Auditors, Equipment suppliers, and R&D Institutions | * The PMU has developed a Forum of stakeholders for awareness * Requested DoI to issue an advisory to all industry associations and concerned department to include sessions green energy financing * Est. contact between industry associations/clusters and SIDBI to promote green energy financing * Made efforts to create a convergence of schemes to promote installation of solar equipment in MSMEs | The PMU has written a letter to the Energy Department, DoI and CREDA for coming up with a favorable policy for developing solar energy hubs/farms in industrial areas on govt. land or through mutual contribution | PMU is making efforts to develop linkages between SIDBI and Industry Associations, CREDA, Energy Auditors, Equipment suppliers, and R&D Institutions to promote Green Energy Financing |  |
| Cluster Financing by facilitating MoU between lead bank/SIDBI and CSIDC to come up with a suitable instrument /model to fund the cluster entities/SPV |  |  | Concept note in this regard has been shared with CSIDC, but still response is awaited  Efforts in this direction is still ongoing | Not executed so far |
| **3** | **Strengthening infrastructure for MSME** | Convergence of GoI/State scheme for MSME – Handholding of one cluster | * Facilitated development of a forging cluster in Raipur under MSE-CDP * Facilitated in submission of 2 SFURTI Cluster Proposals | 4 Proposed clusters are identified but approval for state govt. contribution is due- under consideration for MSE-CDP Scheme | 2 SFURTI Clusters development projects have been sanctioned and being facilitated by PMU |  |
| **4** | **Partnership of State Govt. & State level Industry Associations with strategic BDS** | Development of MSME Facilitation Centre for BDS support to MSMEs through up-gradation of DICs into facilitation centres, particularly for undertaking cluster development activities | * Facilitated meetings with SIDBI and Industry Associations | * Arranged partnership with GTO for preparing export related research based documents * Arranged productive partnerships with FIs, Private Sector buyers, e-commerce partners | Facilitated State Govt. in developing a proposal for development of a silk park in collaboration with HINDALCO |  |
| **5** | **Institutional Strengthening & Capacity Building of stakeholders** | Conduct of BMO capacity building programmes to make them self-sustainable and active in cluster development | Conducted an Offline BMO capacity building Programme |  |  |  |
| Orientation Programme on MSME Ecosystem Development | PMU conducted 2 Orientation Programme on MSME Ecosystem | 1 Proposal for state level Orientation Programme on MSME Ecosystem |  |  |
| Training of DIC Officials on Export Facilitation | 2 Trainings were organized for DIC officials and MSMEs in Raipur and Durg |  |  |  |
| **6** | **Entrepreneurship Development and employment generation** | Development of state's action plan for creation of new MSME units | * Conducted orientation programme for Incubators * Bank linkage programme for start-ups * Facilitated CII in conducted Industry-academia Meet at NIT Raipur | Prepared proposal for establishment of CED by Chhattisgarh state govt. –due for further approval by CM office |  |  |
| Udyam Registration Facilitation |  |  | PMU has arranged for an Udyam Registration Facilitation camp for Kosa artisans in Janjgir-Chapa with support of HINDALCO CSR team in March |  |
| Strategy Development Climate Resilient Entrepreneurship Development and Job Creation | * Organized workshops in collaboration with KREA University on Net Zero Industrial Policy |  | Conference on Climate Change Adaptations and resilience is scheduled on 17/3/2023 |  |
| **7** | **SCDF related intervention** | Promote SCDF to various departments for promoting infrastructure development in MSME clusters | * PMU organized meeting of SIDBI and State Finance department for SCDF * PMU has visited prospective depts. And requested for proposals | The File for SCDF Master Agreement, 293 approval is due for signature by Secretary Finance | Regular follow-ups are being done by the PMU for SCDF Master Agreement, 293 approval |  |
| **8** | **Other** | SIDBI Project Care | PMU conducted primary research for identification of cluster and requested BO for undertaking the project |  |  | PMU was informed that Project Care was not part of their mandate |
| Any task/work assigned by SIDBI/ State MSME Dept. | Support provided to state govt. in day to day activities  Submission of proposals for state MSME award, State level CGTMSE Scheme, MSME Facilitation Centre  Conducted export preparedness gap study and developed a excel template for further use |  |  |  |

**Contact us**

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*