

Fortnightly Report

SIDBI – PMU Tamil Nadu

Period – 01st February to 15th February 2023

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Tamil Nadu**  **Month & Year: February 2023**  **Fortnight Ending: 15th February 2023** | **Report Summary**  **This Report includes the activities carried out by SIDBI - PMU for the facilitation of MSME Ecosystem in the State of Tamil Nadu.** |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | PMU Manager | P. Ganesh | 14th March 2022 |
| 2 | Business Analyst | Hariharan P | 8th December 2020 |

**Details of State Nodal Connect - Ms. Sigy Thomas Vaidhyan (IAS), Commissioner and Director of Inds. & Commerce**

**Email Id:** [**indcomchn@gmail.com**](mailto:indcomchn@gmail.com)

**Activities performed by PMU during fortnight ending 15th February 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| **General Activities to facilitate project implementation** | |
| 1. Discussions held with Under Secretary – MSME; and Under Secretary – Industries with regard to SCDF proposals pending with them. Proposals have now been forwarded to Finance Department. | |
| 1. Undertaken visit to Ambattur alongwith AGM, SIDBI in connection with MSE-CDP proposal for upgradation of infrastructure submitted by TANSIDCO and report submitted. | |
| 1. Completed appraisal of Upgradation project of Ambattur Industrial Estate of TANSIDCO under MSE-CDP Scheme. | |
| 1. Discussions held with Additional Secretary (Finance) alongwith GM of SIDBI in connection with SCDF proposals. | |
| 1. Compiled data and prepared presentation for GM, SIDBI for meeting between Honourable FM of TN and CMD of SIDBI. | |
| 1. Follow-up visit undertaken and reports prepared in respect of SCDF proposals viz., Ambattur Workers’ Hostel and Plug and Play Flatted Factory projects of TANSIDO. The application of TANSIDCO requesting for subsequent disbursement in lieu of expenses already incurred in these projects are expected from Finance Department. | |

|  |
| --- |
| **Actionable and Support required** |
| 1. Awaiting CDV’s decision on whether to take up additional work suggested by ICDIC. |
| **Activities Way forward** |
| 1. To obtain 4 applications submitted by TIDEL Park Ltd., to Finance Department for loans under SCDF. 2. To obtain 3 applications submitted by SIPCOT to Finance Department for loans under SCDF |
| **Inputs of State Nodal Connect / Officer** |
| 1. Industries Commissioner, Government of Tamil Nadu in the feedback letter to DMD, SIDBI on the performance of PMU has suggested that PMU may support ICDIC / FaMe-TN by sharing some more work with them. Awaiting CDV’s instructions. |

**Annexures (viz. Govt. officials, Bankers, Industry Associations contacted, compendium, units visited for rehabilitation/restructuring, etc.)**

|  |
| --- |
| **Annexures** |
|  |

\*\*\*\*\*\*\*\*\*\*

**Contact us**

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad – 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*