

Fortnightly Report

SIDBI – PMU Tamil Nadu

Period – 16th January to 31st January 2023

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Tamil Nadu**  **Month & Year: January 2023**  **Fortnight Ending: 31st January 2023** | **Report Summary**  **This Report includes the activities carried out by SIDBI - PMU for the facilitation of MSME Ecosystem in the State of Tamil Nadu.** |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | PMU Manager | P. Ganesh | 14th March 2022 |
| 2 | Business Analyst | Hariharan P | 8th December 2020 |

**Details of State Nodal Connect - Ms. Sigy Thomas Vaidhyan (IAS), Commissioner and Director of Inds. & Commerce**

**Email Id:** [**indcomchn@gmail.com**](mailto:indcomchn@gmail.com)

**Activities performed by PMU during fortnight ending 31st January 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| **General Activities to facilitate project implementation** | |
| 1. Discussions held with Finance Department, GoTN with regard to SCDF - Two sanction letters issued (Setting up of Plug and Play Flatted Factory Modules in Ambattur, Chennai – Additional Loan; and Workers’ Hostel, Coimbatore – Shifted to Kuruchi). | |
| 1. Discussions held with MD, TANSIDCO alongwith GT Central Team official in connection with inviting her for the Conference on “Tamil Nadu – Towards a Trillion Dollar Economy by 2030 – Evolving an Enabling Ecosystem” organized by ASSOCHAM with Grant Thornton as Knowledge Partner. | |
| 1. Discussions held with MD, Tamil Nadu Skill Development Corporation of Tamil Nadu alongwith GT Central Team official in connection with inviting her for the Conference on “Tamil Nadu – Towards a Trillion Dollar Economy by 2030 – Evolving an Enabling Ecosystem” organized by ASSOCHAM with Grant Thornton as Knowledge Partner. | |
| 1. Visited Karaikal and Chidambaram alongwith GM, SIDBI in connection with SCDF proposals. | |
| 1. Visited the Hon’ble Finance Minister of Tamil Nadu along with ASSOCHAM officials and Grant Thornton Central Team Official in connection with inviting him as Guest of Honour for the Conference on “Tamil Nadu – Towards a Trillion Dollar Economy by 2030 – Evolving an Enabling Ecosystem” organized by ASSOCHAM with Grant Thornton as Knowledge Partner. | |
| 1. Attended the Conference on "Tamil Nadu - Towards a Trillion Dollar Economy by 2030 - Evolving an Enabling Eco-system" organised by ASSOCHAM with Grant Thornton as Knowledge Partner. | |

|  |
| --- |
| **Actionable and Support required** |
| 1. TANSIDCO to submit additional information called for in respect of 1 MSE-CDP proposal. |
| **Activities Way forward** |
| 1. To complete appraisal of 1 MSE-CDP proposals. |
| 1. To obtain 4 applications submitted by TIDEL Park Ltd., to Finance Department for loans under SCDF. |
| **Inputs of State Nodal Connect / Officer** |
| NIL |

**Annexures (viz. Govt. officials, Bankers, Industry Associations contacted, compendium, units visited for rehabilitation/restructuring, etc.)**

|  |
| --- |
| **Annexures** |
|  |

\*\*\*\*\*\*\*\*\*\*

**Contact us**

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad – 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*