

Bi-Monthly Progress Report

(Dec’22 – Jan’23)

SIDBI – PMU Bihar

Project Progress Report – December’22- January’23

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Bihar**  **Month & Year: January 2023**  **For the Period Ending: 31st January, 2023** | **Report Summary**  This Report includes the activities carried out by SIDBI - PMU for the  facilitation of MSME Ecosystem in the State of Bihar |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | Project Manager | Swati Singh | 1st June 2022- 6th Jan’2023 (old) |
| 2 | Project Manager | Ravi Kant Bharti | 16th January 2023 (new) |
| 2 | Business Analyst | Preeti Shree | 16th August 2022 |

**Details of State Nodal Connect –**

**From SIDBI -** Mr. Pradeep Kumar Jha, SIDBI

**From Industries, GoB:** Mr. Pankaj Dixit, Director Industries

**Improved Governance framework/ Policy Advocacy**

* Prepared comparison sheet for different cluster-based schemes. Identified Cluster based schemes and going through the details to differentiate framework designed. Connecting schemes with most relevant scopes and implementation.
* Compendium of schemes booklet preparation for the MSME

**Enhancing Credit flow to MSMEs**

* Arrangement with NBFCs- Figuring out the top ranked NBFCs operational in Bihar. Three (IIFL Samasta Finance Ltd, Annapurna Finance & L&T Finance of concerned interested in further communication and looking forward in regard of the Co-lending Finance.
* Connecting to NGOs/ Similar operational organization to find out the Livelihoods Finance or promotion of microenterprise development. Also, in the conversation with Bihar-State Rural Livelihoods Mission. Coordination with SEWA Bharat to work on women entrepreneur specific project by collaboration with SIDBI schemes has been facilitated.

**Strengthening Infrastructure for MSMEs**

* Supported Department of Industries in drafting co-working space ToR in the Start-up perspective.
* Support to Academic Institutions such as CIMP for establishing MSME-Incubation cell. Also, working on scope of similar establishment in other institutions.
* Drafted proposal for Strengthening of Institutes of Entrepreneurship Development (IED), Bihar to assist Department of Industries
* There was a proposed format to be prepared for monthly meeting of GM-DICs. PMU team have prepared the data and raking metrics for different ongoing schemes in the Department of Industries.
* Representing the State in Chief Secretary Conference for strengthening the MSME ecosystem. Prepared a detail document on this as well as Survey has been done.
* Meeting with Director Food processing for finalisation of TOR for PMFME scheme and its execution.
* PMU supported in MSE-CDP proposals. Appraisals from SIDBI and SLCC meeting also completed. Coordination and follow up with SIDBI for receiving the final copy so, that it could be uploaded by PMU to complete the procedure.
* Working on proposals drafting for CFC projects (textile & metal clusters) with DOI and scoping it with SIDBI where working capital support could be a visible indicator.
* RAMP- Government has launched a World Bank supported Central Sector Scheme called Raising and Accelerating MSME Performance (RAMP).  The scheme aims at strengthening institutions and governance at the Centre and State, improving Centre-State linkages and partnerships, and improving access of MSMEs to market and credit, technology upgradation and addressing issues of delayed payments and greening of MSMEs. In the further process prepared detail document for roadmap of Diagnostic study, ToR for SPIU formation. Coordination for the same to publish on the DOI website. In the meanwhile, supported for CNA account opening for RAMP. Meeting with Central University, BIA and CIMP as part of RAMP Diagnostic Study.
* RAMP- PMU assisted in conducting pre-liminary interview and snapshot of data preparation for candidates with DOI.
* New phase of account opening and SNA-CNA account mapping for RAMP with Axis Bank.
* SFURTI Scheme- PMU assigned as the Nodal for the scheme. Various level of meetings such as with Assistant Director (Handloom), KVIC, EPCH, Department of Handloom & Sericulture and MSME Department for discussing the steps to be implemented, identification of clusters. Seven Concept Note prepared by PMU in coordination with Departments (Handloom & Handicraft) and submitted to the Nodal Agency. Following up with the Nodal Agency for further procedures. Total 12 concept notes have been prepared and uploaded.
* Coordinated and completed the meeting with Director Industries, Director Handloom and Director KVIC for finalising the technical agency. NIFT Kolkata has been selected as Technical Agency and coordinating for further preparation of DPRs for 3 concept proposals.
* Two new concept proposal has been recently prepared and submitted under SFURTI.
* Handholding support to Jeevika for SFURTI scheme.
* Meeting with Jeevika for the convergence related indicators of Department of Industries. Bag cluster coordination was already in process and now supporting for developing one metal cluster.
* Meeting with Jeevika officials for extension of SIDBI support under Prayaas Scheme. Seeking for the meeting appointment with CEO-Jeevika for bringing it to implementation level.

**Institutional Strengthening and Capacity Building of Stakeholders**

* PMU team assisted Department in opening CNA account for TIES Scheme.
* MSEFC Council is one of the parts of DOI to deal with court cases. PMU team continuously supporting in drafting the details as asked by Director Industries.
* Prepared data regarding budget 2022-23 on behalf of DOI to Finance Department.
* Supported in Orientation of District Development Officer (DDC) for MSMEs Schemes and convergence through presentation, Brochure preparation and data.
* Preparing training calendar for various schemes under different stakeholders of DoI and SIDBI.
* PMU also supported DOI for different Banker’s level meeting with data, report, and presentations time to time. Such meeting also includes Mega Bank Camps, SLBC, Specific Bank higher officials, Bankers meet.
* Coordinated and completed ZED training for GM-DICs and IEOs. Implementing ZED scheme with benefits in the industrial policy- discussion with the central team and proposed to industries so that we could work on draft.

**Entrepreneurship Development and Employment generation**

* Supported in the evaluation process of new 200 applications of start-ups under Bihar Start Up Policy 2022.
* Supported in the Start-Up event planning at college campus for awareness.
* Start-up support to department for finalising beneficiaries for next round of seed fund
* Support in organising and coordinating Awareness camp for start-up/MSMEs in colleges
* Coordination for start-up online examination
* Start-Up seed fund tranche disbursement under New Bihar Start-Up Policy.
* Interacted with Entrepreneurs related to textile for handhold support
* Supporting and Liasoning with Start-up team (DOI) for MOU between SIDBI and DOI for Start-up funding (AIF). In this regard a meeting with start-up team has been done and trying to get it done through DOI in next coming weeks. Final draft also processed through file for approval.

**SCDF**

* The proposal has been submitted by Department of Industries and Department of Roads for 350 Crores and 174 Crores respectively, but the approval from Finance Dept is still awaited
* Initial Meeting on orientation of SCDF has been done with departments - PHED, S&T
* SCDF Orientation started by PMU - Department of Skill development for training lab, Dept of Fisheries for cold storage, Dept of Cooperative for Haat / Cold storage

**Others**

* There are ongoing review meetings/discussions, report preparation and presentation by GT and SIDBI. Actively participation in all is a major task.
* DOI asked the PMU team for drafting the Caselet of different success stories of related ongoing schemes. 6 case studies drafted and shared.
* Prepared Presentation and Report for Industrial Corridor for CM-Bihar.
* MSME Review Meetings with PS and Review Meeting by Department
* Supporting DOI on a report where impact could be seen through policies and data.
* DIC ranking data and presentation prepared by PMU
* PMEGP-Bank & District wise data preparation
* PMEGP/PMFME bank wise data preparation for review.
* Chief Secretary review data and ppt presentation.

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad - 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park,  Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East,  Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In the context of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBI Vision 2.0 which envisages an integrated credit and development support role of the Bank by being a thought leader, adopting a credit-plus approach, creating a multiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*