

FortnightlyReport

SIDBI – PMU West Bengal

Period–01st -15th December 2022

**Project Progress Report–Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU–MSMEs** | |
| **Location: Kolkata**  **Month & Year: December 2022**  **Fortnight Ending: 15th December 2022** | **ReportSummary**  This Report includes the activities carried out by SIDBI-PMU for the  Facilitation of MSME Ecosystem in the State of West Bengal. |

**TeamDeploymentStatus**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Nameof Resource** | **DeploymentDate** |
| 1 | PMU Manager | Kaushik Mukherjee | 20th Jan 2022 |
| 2 | Business Analyst | Santanu Karmakar | 27th June 2022 |

**Details of State & SIDBI Nodal Connect –**

**Name–Ms. Maitreyee Ganguly, Joint Secretary; Dpt. of MSME&T, Mobile: 8910400819. Email:** [**heremaitreyee@gmail.com**](mailto:heremaitreyee@gmail.com) **and Mr. Siddhartha Mandal, AGM, KOL, Mobile: 8469372214, Email:** [**smandal@sidbi.in**](mailto:smandal@sidbi.in)

**Activities performed by PMU during fortnight ending 15th December 2022**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| **General Activities to facilitate project implementation** | |
| 1. **Improved Governance framework / policy advocacy-** 2. The SIDBI PMU team has evaluated West Bengal Clusters and preparing a detail Cluster compendium report. Upon finalization, the same will submit to the Department of MSME & T. | |
| 1. **Enhancing credit flow to the MSME sector**– 2. The PMU team has initiated the base conversation with the Joint Director of MSME for a strategic tie up with SIDBI for funding proposals that come from Finance Clinic from all the DICs. To initiate the activity, a meeting has been finalized with GM-DIC of Howrah with SIDBI BO which shall take place at third week of December 2022. | |
| 1. **Strengthening infrastructure for MSMEs-** 2. The SIDBI PMU team has supported DIC Howrah to finalize and publish e-tender for Howrah Zari Cluster Plant & Machinery. 3. The PMU team has facilitated handholding support and technical guidance, for setting up and upgrading state-financed cluster CFCs in Janbazar Shoe Cluster, Kaliagunj edible oil cluster and Kenjikura brass and bell metal cluster. | |
| 1. **Partnership of State Govt. & State level Industry Associations with strategic BDS-** 2. The PMU team has started initial discussion with West Bengal Hosiery Association for formalized their CFC proposal to the Department | |
| 1. **Institutional Strengthening & Capacity Building of stakeholders-** 2. The PMU team is technically supporting the Directorate of Textiles to standardize the machine requirement, seeking quotations from reputed vendors, and E-tendering process for procurement of machines to prepare RMG project proposal. | |
| 1. **Promote Entrepreneurship Development, employment generation, responsible business operations-** 2. PMU team facilitated MSME DI to arrange a 5 days MDP on Marketing in association with St. Xavier’s University; Kolkata held in university campus from 5th December to 9th December 2022. The program has been successfully completed and around 25 candidates from various background has been trained on different aspects on modern marketing. | |
| 1. **SIDBI Cluster Development Fund proposals –** 2. Total 15 projects and an amount of approximately 154 Cr. has been sanctioned under SCDF. LoI for all sanctioned projects has been received and forwarded to Finance department. 3. 6 proposals amounting approximately 53 Cr. is under SIDBI appraisal process. Appraisal visit has been completed for 3 projects. 4. Further list of projects is in consideration of the Department for submitting to FD for administrative approval 5. **Meeting Details:** 6. The PMU team attended SIDBI CGM review meeting on 02.12.2022 with regarding West Bengal PMU activities. CGM Sir expressed satisfaction and the meeting ends with some positive notes. 7. The PMU team has visit to SIDBI for administrative discussion on 05.12.2022. 8. The PMU team has attended meeting with Joint Secretary regarding project status indicated in “Sammanway” portal on 05.12.2022. 9. The PMU team has attended meeting with Special Secretory regarding Bantala project status update on 06.12.2022. 10. The PMU team has attended Inauguration of MDP program conducted by MSME-DFO in St. Xavier’s University, Kolkata on 05.12.2022. 11. The PMU team attended meeting with WBSIDCL regarding work status of Ambari-Falakata and Asansol IP on 05.12.2022. 12. The PMU team attended a meeting with FD to follow up on disbursement on 06.12.2022. 13. The PMU team attended a meeting with the Deputy Director of MSME DI regarding EDP and other programs on 06.12.2022 14. The PMU conducted a visit to Jafarnagar Silver Jewellery Cluster on 07.12.2022. Team Collected data on DPR Vetting status, Land condition and current business situation. The project is supposed to be financed by SCDF. 15. The PMU team discussed with Special Secretory and WBSIDCL regarding LOI and modified fund requirement status on 07.12.2022. 16. The PMU has followed up activities with the RMG project with Joint Secretary and Directorate of Textiles on 08.12.2022. 17. The PMU team has attended a meeting with MSME DFO Deputy Director regarding Green project Initiatives and Export Facilitation taken from Kolkata DFO on 09.12.2022. 18. The PMU team has attended a meeting with Joint Director MSME regarding the pending vetting of DPRs on 09.12.2022. 19. The PMU team has attended a meeting with WBSIDCL regarding the new fund request e-filing to the Department on 09.12.2022. 20. The PMU team has conducted meeting with the Superintendent Engineer of KMDA regarding the Bantala Storm Water Drainage Project and Additional Road Network Project on 12.12.2022. 21. The PMU team has conducted meeting with Joint Director MSME regarding the work status of the Baruipur Surgical Cluster Project on 12.12.2022. 22. The PMU team has attended a meeting with the Fan manufacturing cluster regarding the machine requirement on 13.12.2022. 23. The PMU team has attended meeting with GM DIC Howrah regarding Zari cluster P&M specification requirement and the upcoming Howrah Synergy program on 13.12.2022. 24. The PMU team has attended meeting with Joint Secretory on 14.12.2022 regarding the last 3 LoI status and submission of 4 LoI which were collected from SIDBI on 13.12.2022. 25. The PMU team has attended another meeting with Joint Secretory regarding the old 3 LoI of March 2022 status on 14.12.2022. 26. The PMU team has conducted a meeting with Directorate and DIC officials regarding the date and time of the SIDBI visit to the Beharampur wooden cluster and Jhalda Selac cluster. PMU team also send the subsequent mail to the Directorate also. | |
| 1. **Others-** 2. The PMU team assisted department officials for preparing document required for PS internal GM Conference. | |

|  |
| --- |
| **Actionable and Support required** |
| 1. Ministry of Finance; Government of WB to provide date for meeting with ACS; Finance |
| **Activities Way forward** |
| 1. Speed up the SCDF Process 2. Other activities for strengthen MSME Eco System in WB – stress to be given for Financial tie ups |
| **Inputs of State Nodal Connect/Officer** |
| 1. To speed up project finalization and tendering related activities |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices asmentionedbelow:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEWDELHI**  National Office,Outer Circle, L 41,Connaught Circus,New Delhi - 110001T+911142787070 | **NEWDELHI**  6thFloor,Worldmark2,Aerocity,  New Delhi - 110037T+911149527400 | **AHMEDABAD**  7thFloor,HeritageChambers,  Nr Azad Society,Nehru Nagar,Ahmedabad-380015 | **BENGALURU**  5thFloor,65/2,BlockA,Bagmane Tridib,Bagmane Tech Park,CV Raman Nagar,Bengaluru-560093  T+918042430700 | **CHANDIGARH**  B-406A, 4th Floor, L&TElante Office Building,IndustrialAreaPhaseI,Chandigarh -160002  T+911724338000 |
| **CHENNAI**  7thFloor,PrestigePolygon,  471, Anna Salai,Teynampet,Chennai-600018  T+914442940000 | **DEHRADUN**  SuiteNo2211,2ndFloor,Building 2000, MichiganAvenue, Doon ExpressBusiness Park,  Subhash Nagar,Dehradun-248002  T+911352646500 | **GURGAON**  21stFloor,DLFSquare,Jacaranda Marg, DLFPhaseII,  Gurgaon- 122002  T+911244628000 | **HYDERABAD**  7th Floor,BlockIII,WhiteHouse,  Kundan Bagh,Begumpet,Hyderabad-500016  T+914066308200 | **KOCH**I  6thFloor,ModayilCentrePoint, Warriam RoadJunction, MGRoadKochi-682016  T+914844064541 |
| **KOLKATA**  10CHungerfordStreet,5th Floor,  Kolkata-700017  T+913340508000 | **MUMBAI**  11thFloor,TowerII,  One International Center,SB Marg Prabhadevi (W),Mumbai-400013  T+912266262600 | **MUMBAI**  Kaledonia,1stFloor,C Wing, (OppositeJ&J Office),  Sahar Road,AndheriEast,  Mumbai-400 069 | **NOIDA**  PlotNo19A,2ndFloor,Sector-16A,  Noida-201301  T+911204855900 | **PUNE**  3rdFloor,UnitNo309-312, West Wing, NyatiUnitree, Nagar Road,Yerwada  Pune-411006  T+912067448800 |

Formoreinformationorforanyqueries,writetousat[**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Followus@GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts asthe Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and MediumEnterprise(MSME)sectoraswellasforco-ordinationoffunctionsofinstitutionsengagedinsimilaractivities.Inthecontext of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBIVision2.0whichenvisagesanintegratedcreditanddevelopmentsupportroleoftheBankbybeingathoughtleader,adoptingacredit-plusapproach,creating amultipliereffectand servingasanaggregatorinMSMEspace.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementingagency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any actiontakenbyitbasedonthisdocument.SIDBI,itsdirectors,employeesoranyofficeshallnotbeliableforlossofwhatsoevernaturearising byusingthecontentofthisdocument.*