

Fortnightly Report

SIDBI – PMU West Bengal

Period–01st - 15th January 2023

**Project Progress Report–Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU–MSMEs** | |
| **Location: Kolkata**  **Month & Year: January 2023**  **Fortnight Ending: 15th January 2023** | **Report Summary**  This Report includes the activities carried out by SIDBI-PMU for the  Facilitation of MSME Ecosystem in the State of West Bengal. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Nameof Resource** | **Deployment Date** |
| 1 | PMU Manager | Kaushik Mukherjee | 20th Jan 2022 |
| 2 | Business Analyst | Santanu Karmakar | 27th June 2022 |

**Details of State & SIDBI Nodal Connect –**

**Name–Ms. Maitreyee Ganguly, Joint Secretary; Dpt. of MSME&T, Mobile: 8910400819. Email:** [**heremaitreyee@gmail.com**](mailto:heremaitreyee@gmail.com) **and Mr. Siddhartha Mandal, AGM, KOL, Mobile: 8469372214, Email:** [**smandal@sidbi.in**](mailto:smandal@sidbi.in)

**Activities performed by PMU during fortnight ending 15th January 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| **General Activities to facilitate project implementation** | |
| 1. **Improved Governance framework / policy advocacy-** 2. SIDBI PMU team is preparing the first draft of the Scheme User Matrix across various departments of the Government of West Bengal. 3. The SIDBI PMU team is working on the North Bengal MSME Map as per the direction of the SIDBI BO. The team has prepared a draft report and shared it with the SIDBI BO for review. | |
| 1. **Enhancing credit flow to the MSME sector**– 2. The SIDBI PMU team has conducted meeting with SIDBI Kolkata BO in charge Mr. S. Mondal regarding upcoming financial awareness training program schedule. 3. The SIDBI PMU team has prepared the MoM between HDFC Bank and GM DIC Nadia. The MoM was shared with GM DIC Nadia for his review; once finalized, it will be shared with the HDFC team. | |
| 1. **Strengthening infrastructure for MSMEs-** 2. Discussion with SIDBI BO on preparing Govt. official list for easiness of communication. Prepared a list of contact details of state government officials and shared it with SIDBI. 3. PMU team attended Khadi Mela and discussed with artisans present there regarding different aspects. | |
| 1. **Institutional Strengthening & Capacity Building of stakeholders-** 2. PMU team has provided retraining and handholding support to Govt. officials to fill up Application Forms and other documents on SCDF. 3. PMU team has assisting DIC Kolkata on preparing technical document for upcoming Bid of Janbazar Cluster. | |
| 1. **SIDBI Cluster Development Fund proposals –** 2. 6 proposals amounting approximately 53 Cr. is under SIDBI appraisal process. Appraisal visit has been completed for 3 projects. 3. Further list of projects worth of nearly 60 Cr. is in consideration of the Department for submitting to FD for administrative approval. 4. Disbursement proposal of mobilization fund of approx. 42 Cr. is with finance department. | |
| 1. **Meeting Details:** 2. The PMU team discussed with WBSIDCL the current issues caused by the submission of the same projects in different schemes on January 3, 2023. 3. The PMU team discussed with the Finance Department to discuss the acceptance of seven letters of intent on January 3, 2023. 4. **The PMU team discussed with GM DIC Howrah the tentative schedule of the financial awareness programme to be conducted in different private IPs in Howrah on January 4, 2023.** 5. The PMU team has discussed with Kolkata DIC about the upcoming project of the Kolkata Misti Hub on April 1, 2023. 6. Meeting with Joint Director Textiles on upcoming projects in Tantuja and Tantushree on January 05, 2023. 7. On January 5, 2023, a meeting with the Joint Director MSME will be held to discuss the prospects of various training programmes in collaboration with various cluster stakeholders. 8. Discussion with the Joint Secretary on the status of projects with DTC on January 6, 2023. 9. Discussion with SIDBI RO and BO officials regarding disbursement status and the upcoming financial awareness training programme schedule on January 6, 2023. 10. On January 9, 2023, there will be a meeting with NSIC Howrah regarding the Cluster Level Technical Awareness Program. 11. Meeting with Special Secretary and updating him on current project status on January 09, 2023. 12. Discussion with the SIDBI BO regarding the preparation of the government's official list for ease of communication on January 9, 2023. 13. Discussion with Joint Director MSME & T regarding clarification of Jhalda and Shantiniketan project on 10.01.2023. 14. **Discussion with Joint Secretary Department of MSME & T regarding the project proposals to be submitted to Finance department for SCDF approval on January 10, 2023.** 15. **Attended meeting of The Science and Technology Entrepreneurs' Park (STEP)-IIT Kharagpur regarding different support procedure for West Bengal MSME on January 11, 2023.** 16. Meeting attended with Special Secretary and other Stakeholders regarding ongoing MSE-CDP projects on January 11, 2023. 17. Discussion with Joint Secretary regarding DTC (Departmental Tender Committee) approval status of Bauriya, Baruipur and Suri project. Follow-up to be done with finance department on January 11, 2023. | |
| 1. **Green Financing-** 2. The SIDBI PMU team is preparing a concept note on the applicability of Green Financing in the MSME sector. | |
| 1. **Others-** 2. PMU team has prepared a Monthly progress report for December 2022 and shared it with GT internal team. 3. The PMU team assisted department officials for preparing document required for PS internal GM Conference. | |

|  |
| --- |
| **Actionable and Support required** |
| 1. Ministry of Finance; Government of WB to provide date for meeting with ACS; Finance |
| **Activities Way forward** |
| 1. Speed up the SCDF Process 2. Other activities for strengthen MSME Eco System in WB – stress to be given for Financial tie ups |
| **Inputs of State Nodal Connect/Officer** |
| 1. To speed up project finalization and tendering related activities |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices asmentionedbelow:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEWDELHI**  National Office,Outer Circle, L 41,Connaught Circus,New Delhi - 110001T+911142787070 | **NEWDELHI**  6thFloor,Worldmark2,Aerocity,  New Delhi - 110037T+911149527400 | **AHMEDABAD**  7thFloor,HeritageChambers,  Nr Azad Society,Nehru Nagar,Ahmedabad-380015 | **BENGALURU**  5thFloor,65/2,BlockA,Bagmane Tridib,Bagmane Tech Park,CV Raman Nagar,Bengaluru-560093  T+918042430700 | **CHANDIGARH**  B-406A, 4th Floor, L&TElante Office Building,IndustrialAreaPhaseI,Chandigarh -160002  T+911724338000 |
| **CHENNAI**  7thFloor,PrestigePolygon,  471, Anna Salai,Teynampet,Chennai-600018  T+914442940000 | **DEHRADUN**  SuiteNo2211,2ndFloor,Building 2000, MichiganAvenue, Doon ExpressBusiness Park,  Subhash Nagar,Dehradun-248002  T+911352646500 | **GURGAON**  21stFloor,DLFSquare,Jacaranda Marg, DLFPhaseII,  Gurgaon- 122002  T+911244628000 | **HYDERABAD**  7th Floor,BlockIII,WhiteHouse,  Kundan Bagh,Begumpet,Hyderabad-500016  T+914066308200 | **KOCH**I  6thFloor,ModayilCentrePoint, Warriam RoadJunction, MGRoadKochi-682016  T+914844064541 |
| **KOLKATA**  10CHungerfordStreet,5th Floor,  Kolkata-700017  T+913340508000 | **MUMBAI**  11thFloor,TowerII,  One International Center,SB Marg Prabhadevi (W),Mumbai-400013  T+912266262600 | **MUMBAI**  Kaledonia,1stFloor,C Wing, (OppositeJ&J Office),  Sahar Road,AndheriEast,  Mumbai-400 069 | **NOIDA**  PlotNo19A,2ndFloor,Sector-16A,  Noida-201301  T+911204855900 | **PUNE**  3rdFloor,UnitNo309-312, West Wing, NyatiUnitree, Nagar Road,Yerwada  Pune-411006  T+912067448800 |

Formoreinformationorforanyqueries,writetousat[**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Followus@GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts asthe Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and MediumEnterprise(MSME)sectoraswellasforco-ordinationoffunctionsofinstitutionsengagedinsimilaractivities.Inthecontext of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBIVision2.0whichenvisagesanintegratedcreditanddevelopmentsupportroleoftheBankbybeingathoughtleader,adoptingacredit-plusapproach,creating amultipliereffectand servingasanaggregatorinMSMEspace.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementingagency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any actiontakenbyitbasedonthisdocument.SIDBI,itsdirectors,employeesoranyofficeshallnotbeliableforlossofwhatsoevernaturearising byusingthecontentofthisdocument.*