

FortnightlyReport

SIDBI – PMU West Bengal

Period–16th - 31st December 2022

**Project Progress Report–Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU–MSMEs** | |
| **Location: Kolkata**  **Month & Year: December 2022**  **Fortnight Ending: 31st December 2022** | **ReportSummary**  This Report includes the activities carried out by SIDBI-PMU for the  Facilitation of MSME Ecosystem in the State of West Bengal. |

**TeamDeploymentStatus**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Nameof Resource** | **DeploymentDate** |
| 1 | PMU Manager | Kaushik Mukherjee | 20th Jan 2022 |
| 2 | Business Analyst | Santanu Karmakar | 27th June 2022 |

**Details of State & SIDBI Nodal Connect –**

**Name–Ms. Maitreyee Ganguly, Joint Secretary; Dpt. of MSME&T, Mobile: 8910400819. Email:** [**heremaitreyee@gmail.com**](mailto:heremaitreyee@gmail.com) **and Mr. Siddhartha Mandal, AGM, KOL, Mobile: 8469372214, Email:** [**smandal@sidbi.in**](mailto:smandal@sidbi.in)

**Activities performed by PMU during fortnight ending 31st December 2022**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| **General Activities to facilitate project implementation** | |
| 1. **Improved Governance framework / policy advocacy-** 2. SIDBI PMU team is preparing the first draft of the Scheme User Matrix across various departments of the Government of West Bengal. | |
| 1. **Enhancing credit flow to the MSME sector**– 2. The SIDBI PMU team has conducted meeting with GM DIC Howrah and SIDBI Kolkata BO in charge Mr. S. Mondal regarding strategic tie-up to increase credit flow to the MSMEs across Howrah district on 22nd December 2022. 3. SIDBI PMU team has attended monthly Financial clinic conducted by DIC Howrah. 4. Discussion held with GM DIC regarding arrangement of Financial Awareness campaign across different private industrial parks in Howrah. 5. The SIDBI PMU team has conducted meeting with Joint Secretory, Department of MSME & T and Mr. Anil Bhavnani Country Head of HDFC Bank, Mr. Venkatesh Challawar a Regional Head of HDFC Bank, and Ms. Vandita Shively a National Lead proposing wider Financial coverage for MSMEs across West Bengal. 6. SIDBI PMU team finalized and conducted meeting with GM DIC Nadia and his officials with Mr. Venkatesh Challawar-Regional Head of HDFC Bank regarding enriching credit flow of MSME clusters at Nadia district on 29.12.2022. | |
| 1. **Strengthening infrastructure for MSMEs-** 2. PMU team has prepared an inspection report of Jafarnagar Silver Jewellery cluster. The report has elaborated about the cluster details, observations, GAP and possible outcome. 3. PMU team has visited Nadia DIC for Cluster and Synergy related issues. Team has detailed discussion with GM and DFO regarding Synergy, which clusters will be shipped for next financial year, Jafarnagar Silver Cluster DPR readiness and current cluster condition of the district. | |
| 1. **Institutional Strengthening & Capacity Building of stakeholders-** 2. PMU team has provided retraining and handholding support to Govt. officials to fill up Application Forms and other documents on SCDF. 3. PMU Team guided DIC Jalpaiguri to set up 5 Industrial Cooperatives with ST Women of Samsing area to take part in RMG Project | |
| 1. **Promote Entrepreneurship Development, employment generation, responsible business operations-** 2. The SIDBI PMU team conducted discussed with MSME DI to arrange different other training programs in partnership with several organizations line R. K. Mission, Techno India etc. in next few months. | |
| 1. **SIDBI Cluster Development Fund proposals –** 2. Total 15 projects and an amount of approximately 154 Cr. has been sanctioned under SCDF. LoI for all sanctioned projects has been received and forwarded to Finance department. 3. 6 proposals amounting approximately 53 Cr. is under SIDBI appraisal process. Appraisal visit has been completed for 3 projects. 4. Further list of projects is in consideration of the Department for submitting to FD for administrative approval. 5. **Meeting Details:** 6. The SIDBI PMU team attended a review meeting with Special Secretory, Joint Secretory, WBSIDCL and WBKVIB on 16.12.2022. 7. The SIDBI PMU team attended a meeting with JD MSME regarding MSE-CDP issues on 16.12.2022. 8. The SIDBI PMU team attended a meeting with meeting with Joint Director MSME regarding projects on hold on 19.12.2022. 9. The SIDBI PMU has a discussion with WBSIDCL on MSE-CDP and SCDF Project anomaly subject to HPC Meeting on 20.12.2022. 10. The SIDBI PMU has a discussion with Joint Secretory on Gatisakti rejected proposals on 20.12.2022. 11. The SIDBI PMU team attended a review meeting of Principal Secretary on different ongoing schemes on 21.12.2022. 12. The SIDBI PMU team conducted meeting with department officials related to projects sanctioned by PM Gatishakti and their fund mobilisation on 21.12.2022. 13. The SIDBI PMU team Conducted a meeting with GM DIC Howrah and SIDBI Kolkata BO in charge Mr. S. Mondal regarding strategic tie-up to increase credit flow to the MSMEs across Howrah district 22.12.2022. 14. The SIDBI PMU team has conducted meeting with GM DIC Howrah and SIDBI Kolkata BO in charge Mr. S. Mondal regarding strategic tie-up to increase credit flow to the MSMEs across Howrah district on 22.12.2022. 15. The SIDBI PMU team has conducted meeting with GM DIC Howrah and SIDBI Kolkata BO in charge Mr. S. Mondal regarding strategic tie-up to increase credit flow to the MSMEs across Howrah district on 22.12.2022. 16. The SIDBI PMU team has arranged meeting with Joint Secretory on Department Tender Committee (DTC) approval status for different projects on 22.12.2022. 17. The SIDBI PMU team has arranged a meeting with Joint Director MSME on participation in a different Synergy program on 23.12.2022. 18. The SIDBI PMU team has attended meeting with KMDA on Bantala upcoming projects and land issues on 23.12.2022. 19. The SIDBI PMU team has attended meeting with Daspara Brass & Bell metal cluster SPV on P&M procurement tendering process on 23.12.2022. 20. The SIDBI PMU team has attended meeting with Finance Department regarding Janbazar Lather Cluster disbursement e-file proceeding. 21. The SIDBI PMU team has attended meeting with KMDA Superintendent Engineer regarding project funding from Budget allocation. 22. The SIDBI PMU team has conducted meeting with HDFC RM regarding meeting finalization with GM of Nadia DIC. 23. The SIDBI PMU team has attended meeting with KMDA SE regarding work completion status of several projects at Bantala and fund disbursement status from Finance Department. 24. PMU team has conducted a meeting with GM DIC Nadia and the Regional Rural Head of HDFC bank with his team regarding enhancing credit flow of MSME sectors. | |
| 1. **Others-** 2. The PMU team assisted department officials for preparing document required for PS internal GM Conference. 3. The SIDBI PMU Team has prepared CY 2022 PMU activity report. After the finalization of the final draft will share it with the Department of MSME & T. 4. **Green Financing:** PMU team has initiated discussion about solar energy plant installation under different units and offices of WBKVIB which may be funded under SIDBI green financing. Convergence possibilities with SCDF may also be explored. | |

|  |
| --- |
| **Actionable and Support required** |
| 1. Ministry of Finance; Government of WB to provide date for meeting with ACS; Finance |
| **Activities Way forward** |
| 1. Speed up the SCDF Process 2. Other activities for strengthen MSME Eco System in WB – stress to be given for Financial tie ups |
| **Inputs of State Nodal Connect/Officer** |
| 1. To speed up project finalization and tendering related activities |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices asmentionedbelow:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEWDELHI**  National Office,Outer Circle, L 41,Connaught Circus,New Delhi - 110001T+911142787070 | **NEWDELHI**  6thFloor,Worldmark2,Aerocity,  New Delhi - 110037T+911149527400 | **AHMEDABAD**  7thFloor,HeritageChambers,  Nr Azad Society,Nehru Nagar,Ahmedabad-380015 | **BENGALURU**  5thFloor,65/2,BlockA,Bagmane Tridib,Bagmane Tech Park,CV Raman Nagar,Bengaluru-560093  T+918042430700 | **CHANDIGARH**  B-406A, 4th Floor, L&TElante Office Building,IndustrialAreaPhaseI,Chandigarh -160002  T+911724338000 |
| **CHENNAI**  7thFloor,PrestigePolygon,  471, Anna Salai,Teynampet,Chennai-600018  T+914442940000 | **DEHRADUN**  SuiteNo2211,2ndFloor,Building 2000, MichiganAvenue, Doon ExpressBusiness Park,  Subhash Nagar,Dehradun-248002  T+911352646500 | **GURGAON**  21stFloor,DLFSquare,Jacaranda Marg, DLFPhaseII,  Gurgaon- 122002  T+911244628000 | **HYDERABAD**  7th Floor,BlockIII,WhiteHouse,  Kundan Bagh,Begumpet,Hyderabad-500016  T+914066308200 | **KOCH**I  6thFloor,ModayilCentrePoint, Warriam RoadJunction, MGRoadKochi-682016  T+914844064541 |
| **KOLKATA**  10CHungerfordStreet,5th Floor,  Kolkata-700017  T+913340508000 | **MUMBAI**  11thFloor,TowerII,  One International Center,SB Marg Prabhadevi (W),Mumbai-400013  T+912266262600 | **MUMBAI**  Kaledonia,1stFloor,C Wing, (OppositeJ&J Office),  Sahar Road,AndheriEast,  Mumbai-400 069 | **NOIDA**  PlotNo19A,2ndFloor,Sector-16A,  Noida-201301  T+911204855900 | **PUNE**  3rdFloor,UnitNo309-312, West Wing, NyatiUnitree, Nagar Road,Yerwada  Pune-411006  T+912067448800 |

Formoreinformationorforanyqueries,writetousat[**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Followus@GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts asthe Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and MediumEnterprise(MSME)sectoraswellasforco-ordinationoffunctionsofinstitutionsengagedinsimilaractivities.Inthecontext of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBIVision2.0whichenvisagesanintegratedcreditanddevelopmentsupportroleoftheBankbybeingathoughtleader,adoptingacredit-plusapproach,creating amultipliereffectand servingasanaggregatorinMSMEspace.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementingagency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any actiontakenbyitbasedonthisdocument.SIDBI,itsdirectors,employeesoranyofficeshallnotbeliableforlossofwhatsoevernaturearising byusingthecontentofthisdocument.*