

Fortnightly Report

SIDBI – PMU West Bengal

Period–16th – 31st January 2023

**Project Progress Report–Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU–MSMEs** | |
| **Location: Kolkata**  **Month & Year: January 2023**  **Fortnight Ending: 31st January 2023** | **Report Summary**  This Report includes the activities carried out by SIDBI-PMU for the  Facilitation of MSME Ecosystem in the State of West Bengal. |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Nameof Resource** | **Deployment Date** |
| 1 | PMU Manager | Kaushik Mukherjee | 20th Jan 2022 |
| 2 | Business Analyst | Santanu Karmakar | 27th June 2022 |

**Details of State & SIDBI Nodal Connect –**

**Name–Ms. Maitreyee Ganguly, Joint Secretary; Dpt. of MSME&T, Mobile: 8910400819. Email:** [**heremaitreyee@gmail.com**](mailto:heremaitreyee@gmail.com) **and Mr. Siddhartha Mandal, AGM, KOL, Mobile: 8469372214, Email:** [**smandal@sidbi.in**](mailto:smandal@sidbi.in)

**Activities performed by PMU during fortnight ending 31st January 2023**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| **General Activities to facilitate project implementation** | |
| 1. **Improved Governance framework / policy advocacy-** 2. As directed by the Department of MSME & T the PMU team is monitoring “Samannay” portal different project details and preparing a month-wise comparative progress report. | |
| 1. **Strengthening infrastructure for MSMEs-** 2. The PMU team prepared and submitted comparative statement of Rate quotations of Janbazar Lather Artisans Cluster machineries to the Department of MSME & T. | |
| 1. **Institutional Strengthening & Capacity Building of stakeholders-** 2. PMU team has provided retraining and handholding support to Govt. officials to fill up Application Forms and other documents on SCDF. 3. PMU team has assisting DIC Kolkata on preparing technical document for upcoming Bid of Janbazar Cluster. | |
| 1. **SIDBI Cluster Development Fund proposals –** 2. Sanctioned has been done and LoI received for three projects. 3. Further list of projects worth of nearly 60 Cr. is in consideration of the Department for submitting to FD for administrative approval. 4. Disbursement proposal of mobilization fund of approx. 42 Cr. is with finance department. | |
| 1. **Meeting Details:** 2. The PMU team has attended the preview meeting of the formalisation of MSME held in the Department of MSME & T on January 17, 2023. 3. The PMU team has a discussion with the finance department regarding disbursement and LoI acceptance status on January 17, 2023. 4. PMU team met with the Janbazar leather cluster and visited the CFC site on January 18, 2023. 5. PMU team has initial discussion with Manager of Kolkata DIC regarding P&M of Janbazar on January 18, 2023. 6. PMU team facilitate Meeting with Janbazar Tender Committee regarding re-vetting of the P&M section from PWD on 19th January 2023. 7. PMU team has attended meeting with Special Secretary regarding different discrepancies in MSE-CDP proposals and other projects, same coordinated with Joint Secretary on 19th January 2023. 8. PMU team has attended meeting with CE PWD mechanical and discussed about the rate vetting process on 20th January 2023. 9. PMU team has attended meeting with DIC Kolkata Manager on P&M bid process for Kumartuli Cluster on 25th January 2023. 10. PMU team has attended meeting with Janbazar Cluster SPV regarding Raw Material Bank formation on 25th January 2023. 11. **The PMU team attended a meeting with CGM SIDBI on January 27th, 2023, regarding the SCDF update status and has a pre-scheduled meeting with ACS Finance.** 12. **The PMU team has discussions with DGM SIDBI on January 27th, 2023, regarding project CARE and a fixed schedule for the SLI Team meeting on February 1, 2023.** 13. **The PMU team attended meeting with the Joint Director MSME & T to discuss the monthly progress of schemes uploaded through the “Samannay” portal on January 30, 2023.** 14. The PMU team has attended a meeting with the GM of DIC Kolkata regarding the preparation of the comparative statement of Rate quotations for Janbazar Lather Artisans Cluster for sending to PWD for vetting purpose on January 30, 2023. | |
| 1. **Green Financing-** 2. The PMU team has prepared the first draft of the list of effective clusters suitable for adopting Green financing from SIDBI. The list shall be submitted to Joint Director of MSME for further discussion with the respective GM-DICs and cluster stakeholders. 3. The SIDBI PMU team is preparing a concept note on the applicability of Green Financing in the MSME sector. | |
| 1. **Others-** 2. PMU team has prepared a Bi-Monthly progress report for December 2022 and January 2023 shared it with GT internal team. 3. The PMU team assisted department officials for preparing document required for PS internal GM Conference. | |

|  |
| --- |
| **Actionable and Support required** |
| 1. Ministry of Finance; Government of WB to provide date for meeting with ACS; Finance |
| **Activities Way forward** |
| 1. Speed up the SCDF Process 2. Other activities for strengthen MSME Eco System in WB – stress to be given for Financial tie ups |
| **Inputs of State Nodal Connect/Officer** |
| 1. To speed up project finalization and tendering related activities |

**Contact us**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices asmentionedbelow:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEWDELHI**  National Office,Outer Circle, L 41,Connaught Circus,New Delhi - 110001T+911142787070 | **NEWDELHI**  6thFloor,Worldmark2,Aerocity,  New Delhi - 110037T+911149527400 | **AHMEDABAD**  7thFloor,HeritageChambers,  Nr Azad Society,Nehru Nagar,Ahmedabad-380015 | **BENGALURU**  5thFloor,65/2,BlockA,Bagmane Tridib,Bagmane Tech Park,CV Raman Nagar,Bengaluru-560093  T+918042430700 | **CHANDIGARH**  B-406A, 4th Floor, L&TElante Office Building,IndustrialAreaPhaseI,Chandigarh -160002  T+911724338000 |
| **CHENNAI**  7thFloor,PrestigePolygon,  471, Anna Salai,Teynampet,Chennai-600018  T+914442940000 | **DEHRADUN**  SuiteNo2211,2ndFloor,Building 2000, MichiganAvenue, Doon ExpressBusiness Park,  Subhash Nagar,Dehradun-248002  T+911352646500 | **GURGAON**  21stFloor,DLFSquare,Jacaranda Marg, DLFPhaseII,  Gurgaon- 122002  T+911244628000 | **HYDERABAD**  7th Floor,BlockIII,WhiteHouse,  Kundan Bagh,Begumpet,Hyderabad-500016  T+914066308200 | **KOCH**I  6thFloor,ModayilCentrePoint, Warriam RoadJunction, MGRoadKochi-682016  T+914844064541 |
| **KOLKATA**  10CHungerfordStreet,5th Floor,  Kolkata-700017  T+913340508000 | **MUMBAI**  11thFloor,TowerII,  One International Center,SB Marg Prabhadevi (W),Mumbai-400013  T+912266262600 | **MUMBAI**  Kaledonia,1stFloor,C Wing, (OppositeJ&J Office),  Sahar Road,AndheriEast,  Mumbai-400 069 | **NOIDA**  PlotNo19A,2ndFloor,Sector-16A,  Noida-201301  T+911204855900 | **PUNE**  3rdFloor,UnitNo309-312, West Wing, NyatiUnitree, Nagar Road,Yerwada  Pune-411006  T+912067448800 |

Formoreinformationorforanyqueries,writetousat[**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Followus@GrantThorntonIN** |

**Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts asthe Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and MediumEnterprise(MSME)sectoraswellasforco-ordinationoffunctionsofinstitutionsengagedinsimilaractivities.Inthecontext of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBIVision2.0whichenvisagesanintegratedcreditanddevelopmentsupportroleoftheBankbybeingathoughtleader,adoptingacredit-plusapproach,creating amultipliereffectand servingasanaggregatorinMSMEspace.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementingagency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any actiontakenbyitbasedonthisdocument.SIDBI,itsdirectors,employeesoranyofficeshallnotbeliableforlossofwhatsoevernaturearising byusingthecontentofthisdocument.*