

Fortnightly Progress Report

SIDBI – PMU Haryana

Period – 16th Feb – 28th Feb 2023

**Project Progress Report – Fortnightly**

|  |  |
| --- | --- |
| **SIDBI State PMU – MSMEs** | |
| **Location: Haryana Month & Year: Feb,2023**  **Fortnight Ending: 28th Feb 2023** | **Report Summary**  This Report includes the activities carried out by SIDBI -PMU for the facilitation of MSME Ecosystem in the State of Haryana |

**Team Deployment Status**

|  |  |  |  |
| --- | --- | --- | --- |
| **Team** | | | |
| **SN** | **Designation** | **Name of Resource** | **Deployment Date** |
| 1 | PMU Manager | Rahul Mohinder | 24 August 2020 |
| 2 | Business Analyst | Prabhat Chaturvedi | 31 July 2021 |

Details of State Nodal Connect – Sh.Shashi Kant, AD- MSME

**Activities performed by PMU for the fortnight ending 28th Feb 2023.**

|  |  |
| --- | --- |
| **Activity** | **Details of activities carried out** |
| **General Activities to facilitate project implementation** | |
| **SCDF – Directorate of MSME**  **Sanctioned amount – Rs.27.65 Cr**. (Rs. 20.96 Crores sanctioned for 8 Mini cluster projects and Rs.6.67 Cr. for 2 MSE-CDP projects.)  The issue of TPN by the Finance department for the disbursement of the Tranche -1 has been initiated for all the 4 sanctioned projects worth Rs. 7.71 Crores. The requisite details from SIDBI have been submitted by the department for the disbursal of Tranche -1.  **SCDF- UHBVNL**  PMU team had discussed the list of proposals under SCDF with Ms. Rachna Garg, Advisor to Director Finance, UHBVNL, for the project list and their approved DPRs. An internal letter was received from UHBVNL addressing their requirement which currently stands at Rs.240 Crores. The PMU team is coordinating and following up with the department.  **Venture Capital Fund**  The SVCL file was sent to the Finance Department, Haryana for obtaining their concurrence over the drawdown schedule and proposal. Once concurrence is obtained, file will be sent to LR for legal vetting of the Contribution Agreement. | |
| **Climate Compatible Growth (CCG) Workshop** on ‘Green Hydrogen’ was scheduled to be undertaken on 1.03.23 in the presence of a delegation from the CCG consisting of officials from the British Deputy High Commission working in the sphere of climate change. PMU briefed the Addl. Director and prepared the briefings and note for the department. The write up is enclosed as **Annex “A”.** | |
| **Carpet Exports Promotion Council (CEPC) Event in Panipat**  CEPC organized a 2-day Seminar on Development and Promotion of Handmade Carpets of Panipat under Capacity Building Programmes of the Department of Commerce, Govt. of India on 16th and 17th February 2023. SIDBI PMU coordinated with CEPC for the participation of SIDBI as a key speaker on the various financing schemes for MSMEs. The PPT from SIDBI has been attached as **Annex “B”.** | |
| **TReDS**  The concurrence from FD has been obtained for entering into MoU with all the 3 firms, simultaneously. Proposed draft MoU for all the three entities has been shared with the LR Department for the legal vetting and approval. Time from Hon’ble CM office shall be sought for the MoU signing once the concurrence from LR is received. | |
| **CGTMSE**  CGTMSE had requested the State Govt of Haryana to form a special scheme for boosting the credit dispensation in Haryana. The meeting with W/ACS(I&C), Haryana and CEO of CGTMSE is scheduled in the last week of March 23. | |
|  | |
| **Other Activities** | |
| Noting on SVCL, TReDS other documents submission to worthy Director General, Directorate of MSME, ACS(I) etc. | |
| **Inputs of State Nodal Connect / Officer** | |
| Satisfactory work by PMU | |

**Annexures**

* Annex A– Climate Compatible Growth (CCG) Workshop write up.
* Annex B- Carpet Exports Promotion Council (CEPC) SIDBI ppt.

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

**Contact us**

To know more, please visit [**www.grantthornton.in**](http://www.grantthornton.in/) or contact any of our offices as mentioned below:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **NEW DELHI**  National Office, Outer Circle, L 41, Connaught Circus, New Delhi - 110001 T +91 11 4278 7070 | **NEW DELHI**  6th Floor, Worldmark 2, Aerocity,  New Delhi - 110037 T +91 11 4952 7400 | **AHMEDABAD**  7th Floor, Heritage Chambers,  Nr Azad Society, Nehru Nagar, Ahmedabad – 380015 | **BENGALURU**  5th Floor, 65/2, Block A, Bagmane Tridib, Bagmane Tech Park, CV Raman Nagar, Bengaluru - 560093  T+91 80 4243 0700 | **CHANDIGARH**  B-406A, 4th Floor, L&T Elante Office Building, Industrial Area Phase I, Chandigarh - 160002  T +91 172 4338 000 |
| **CHENNAI**  7th Floor, Prestige Polygon,  471, Anna Salai, Teynampet, Chennai - 600018  T +91 44 4294 0000 | **DEHRADUN**  Suite No 2211, 2nd Floor, Building 2000, Michigan Avenue, Doon Express Business Park, Subhash Nagar, Dehradun - 248002  T +91 135 2646 500 | **GURGAON**  21st Floor, DLF Square, Jacaranda Marg, DLF Phase II,  Gurgaon - 122002  T +91 124 462 8000 | **HYDERABAD**  7th Floor, Block III, White House,  Kundan Bagh, Begumpet, Hyderabad - 500016  T +91 40 6630 8200 | **KOCH**I  6th Floor, Modayil Centre Point, Warriam Road Junction, MG Road Kochi - 682016  T +91 484 406 4541 |
| **KOLKATA**  10C Hungerford Street, 5th Floor,  Kolkata - 700017  T +91 33 4050 8000 | **MUMBAI**  11th Floor, Tower II,  One International Center, SB Marg Prabhadevi (W), Mumbai - 400013  T +91 22 6626 2600 | **MUMBAI**  Kaledonia, 1st Floor, C Wing, (Opposite J&J Office),  Sahar Road, Andheri East, Mumbai - 400 069 | **NOIDA**  Plot No 19A, 2nd Floor, Sector - 16A,  Noida - 201301  T +91 120 485 5900 | **PUNE**  3rd Floor, Unit No 309- 312, West Wing, Nyati Unitree, Nagar Road, Yerwada  Pune - 411006  T +91 20 6744 8800 |

For more information or for any queries, write to us at [**contact@in.gt.com**](mailto:contact@in.gt.com)

|  |  |
| --- | --- |
| Twitter-outline | **Follow us @GrantThorntonIN** |

# **Small Industries Development Bank of India (SIDBI),** established under an Act of Parliament in 1990, acts as the Principal Financial Institution for Promotion, Financing and Development of the Micro, Small and Medium Enterprise (MSME) sector as well as for co-ordination of functions of institutions engaged in similar activities. In thecontext of the changing MSME lending landscape, the role of SIDBI has been realigned through adoption of SIDBIVision 2.0 which envisages an integrated credit and development support role of the Bank by being athought leader,adopting a credit-plus approach, creating amultiplier effect and serving as an aggregator in MSME space.





***Disclaime****r: This document is prepared under SIDBI intervention in which Grant Thornton Bharat LLP is the implementing agency. The document users/third parties shall verify the facts and figures at their end and shall be solely liable for any action taken by it based on this document. SIDBI, its directors, employees or any office shall not be liable for loss of whatsoever nature arising by using the content of this document.*

D:\Grant Thornton Bharat\Letterheads GTB\Logo.png© 2020 Grant Thornton Bharat LLP. All rights reserved.

“Grant Thornton Bharat” means Grant Thornton Advisory Private Limited, the sole member firm of Grant Thornton International Limited (UK) in India, and those legal entities which are its related parties as defined by the Companies Act, 2013, including Grant Thornton Bharat LLP.

Grant Thornton Bharat LLP, formerly Grant Thornton India LLP, is registered with limited liability with identity number AAA-7677 and has its registered office at L-41 Connaught Circus, New Delhi, 110001.

References to Grant Thornton are to Grant Thornton International Ltd. (Grant Thornton International) or its member firms. Grant Thornton International and the member firms are not a worldwide partnership. Services are delivered independently by the member firms.